## Dashboard
Seventh Sky Air Conditioning Solutions - CRM Workflow Blueprint
Metric | Target / Tracking | Recommended CRM Modules
Active Leads | From Client Master Register | Lead Management | Client enquiry, status, follow-up, source tracking
Active Projects | From Project Register | Provider Management | Compliance, capability, insurance, territory control
AMC Contracts | From AMC Register | Work Orders | Auto-generated provider assignment and scope control
Open Service Requests | From Service Request Register | Installation/Repair/AMC | Track all service types separately with statuses
Open Complaints | From Complaint Register | Warranty & Complaints | Warranty expiry, claims, incidents, complaint resolution
Provider Compliance | From Provider Compliance Register | Finance | Deposit, progress payment, provider payout, Seventh Sky fee
Cumilla Territory Compliance | From Cumilla Exclusivity Register | Dashboards | Operational, financial, provider, compliance, AMC dashboards

## Provider Master Register
Provider ID | Business Name | Contact Person | Mobile | Email | Service Categories | Coverage Area | Cumilla Exclusivity Signed | Master Agreement Status | Insurance Status | Compliance Status | Assigned Manager | Notes
AC-P001 | Sample AC Contractor Ltd | Provider Contact | 01XXXXXXXXX | provider@example.com | Installation, Maintenance, Repair | Dhaka, Cumilla via Seventh Sky | Yes | Active | Verified | Compliant | Operations Manager | Approved provider
AC-P002 | Sample Cooling Services | Provider Contact | 01XXXXXXXXX | provider2@example.com | Cleaning, Gas, Emergency | Chattogram, Cumilla via Seventh Sky | Yes | Pending | Pending | Under Review | Provider Manager | Awaiting insurance

## Provider Compliance Register
Provider ID | Compliance Item | Required | Document / Evidence | Issue Date | Expiry Date | Verified By | Verification Date | Status | Follow-Up Action
AC-P001 | Trade Licence | Yes | Trade Licence Copy |  |  | Provider Manager |  | Verified | Renew annually
AC-P001 | Company Registration | Yes | Registration Certificate |  |  | Provider Manager |  | Verified | Keep on file
AC-P001 | TIN | Yes | TIN Certificate |  |  | Accounts |  | Verified | Keep on file
AC-P001 | Electrical Safety Competency | Yes | Technician certificates |  |  | Operations |  | Pending | Collect before assignment
AC-P001 | Refrigerant Handling Competency | Yes | Gas handling training evidence |  |  | Operations |  | Pending | Collect before gas work
AC-P001 | Safety Training | Yes | Training record |  |  | Operations |  | Pending | Annual update required

## Provider Insurance Register
Provider ID | Insurance Type | Required | Policy Number | Insurer | Coverage Amount | Expiry Date | Verified | Reminder Date | Remarks
AC-P001 | Public Liability | Yes |  |  | BDT ______ |  | No |  | Mandatory before work
AC-P001 | Workers Compensation | If applicable |  |  | BDT ______ |  | No |  | Required if provider has staff
AC-P001 | Contractor Insurance | Yes |  |  | BDT ______ |  | No |  | Mandatory
AC-P001 | Vehicle Insurance | If vehicle used |  |  | BDT ______ |  | No |  | For transport/service vans
AC-P001 | Product Liability | Optional |  |  | BDT ______ |  | No |  | Recommended for component supply

## Provider Capability Matrix
Provider ID | Residential Consultation | Commercial Consultation | Split AC Installation | Inverter AC Installation | Smart AC Installation | Multi-Zone Installation | Commercial Installation | Relocation | Preventive Maintenance | Corrective Repair | Component Replacement | Chemical Cleaning | Gas / Refrigerant | AMC | Emergency Service | Smart Climate Control
AC-P001 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
AC-P002 | Yes | No | No | No | No | No | No | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | No

## Cumilla Exclusivity Register
Provider ID | Provider Name | Cumilla Clause Signed | Briefing Date | Acknowledgement Evidence | Allowed to Work in Cumilla Independently? | Referral Obligation | Breach Risk | Monitoring Notes
AC-P001 | Sample AC Contractor Ltd | Yes |  | Signed Master Agreement | No | All Cumilla enquiries must be referred to Seventh Sky | Low | Monitor advertising and client referrals
AC-P002 | Sample Cooling Services | Pending |  | Pending Agreement | No | No direct quote/marketing in Cumilla | Medium | Do not assign until signed

## Work Order Register
Work Order No | Project ID | Client ID | Client Name | Provider ID | Service Type | Site Address | Issue Date | Accepted Date | Start Date | Target Completion | Status | Project Value | Provider Fee | Seventh Sky Fee | Warranty Required | Special Conditions
AC-WO-0001 | AC-PRJ-0001 | AC-C001 | Sample Client | AC-P001 | Split AC Installation | Cumilla |  |  |  |  | Draft | BDT 120,000 | BDT 95,000 | BDT 25,000 | Yes | Cumilla exclusivity applies
AC-WO-0002 | AC-PRJ-0002 | AC-C002 | Sample Business Client | AC-P002 | Emergency Repair | Cumilla |  |  |  |  | Pending Acceptance | BDT 15,000 | BDT 10,000 | BDT 5,000 | Repair warranty | Urgent job

## Provider Workflow Detailed
Phase | Step No | Workflow Step | Detailed Task / Activity | Responsible Person | CRM Record Required | Document / Evidence | Decision / Approval Point | Automation Opportunity | Output
Provider Onboarding | 1 | Provider Application | Collect business profile, contact details, service categories and coverage area. | Provider Manager | Provider Master Register | Business profile | Proceed / Reject | Auto-create provider ID | Provider profile created
Provider Onboarding | 2 | Capability Assessment | Assess technical capability for installation, repair, cleaning, gas and AMC services. | Operations Manager | Capability Matrix | Capability checklist | Approve service categories | Dropdown capability matrix | Capability approved
Compliance | 3 | Document Verification | Verify trade licence, company registration, TIN, insurance and safety evidence. | Provider Manager | Provider Compliance Register | Licence and certificates | Compliant / Conditional / Reject | Expiry reminders | Compliance status recorded
Contracting | 4 | Master Agreement | Send and collect signed Master Service Delivery Provider Agreement. | Management | Master Agreement Register | Signed agreement | Approval required | E-sign workflow | Provider legally onboarded
Territory Protection | 5 | Cumilla Briefing | Explain Cumilla exclusivity, non-circumvention and protected client clauses. | Management | Cumilla Exclusivity Register | Signed acknowledgement | Must be signed | Compliance reminder | Provider accepts territory rules
Project Allocation | 6 | Review Client Scope | Review client request and match with provider capability and availability. | Operations Coordinator | Service Request Register | Client request | Provider selection | Auto-match by service area | Provider selected
Project Allocation | 7 | Issue Work Order | Prepare and issue work order with scope, pricing, timeline and warranty terms. | Operations Coordinator | Work Order Register | Work Order | Provider acceptance | Auto-populate work order | Work order issued
Service Delivery | 8 | Site Assessment | Provider attends site, confirms scope, risks, materials and timeline. | Provider | Site Assessment Register | Site report/photos | Variation required? | Mobile upload | Site assessment completed
Service Delivery | 9 | Service Execution | Complete installation, repair, cleaning, gas, AMC or emergency service. | Provider | Project Register | Before/after photos | Quality check required | Progress status update | Service delivered
Quality Assurance | 10 | Completion Review | Review report, photos, client satisfaction and warranty obligations. | Operations Manager | Completion Register | Completion report | Approve completion | Completion checklist | Project ready to invoice
Financial | 11 | Invoice & Payment | Confirm invoice, provider fee, Seventh Sky fee and payment milestones. | Accounts | Invoice & Payment Register | Invoice/receipt | Pay / Hold | Auto payment reminder | Financial closure
Post-Service | 12 | Warranty & AMC Tracking | Record warranty, AMC schedule, future service date and complaint process. | Coordinator | Warranty/AMC Register | Warranty record | Ongoing support | Auto service reminders | Lifecycle support activated

## Provider Checklist
Checklist Category | Checklist Item | Required? | Frequency | Responsible | Evidence Required | Pass Criteria | CRM Sheet | Status
Legal | Signed Master Agreement | Yes | Before first job | Management | Signed agreement | Agreement signed by authorised person | Master Agreement Register | Pending
Legal | Cumilla Exclusivity Acceptance | Yes | Before Cumilla job | Management | Signed acknowledgement | Clause accepted | Cumilla Exclusivity Register | Pending
Compliance | Trade Licence Verified | Yes | Annual | Provider Manager | Licence copy | Valid and current | Provider Compliance Register | Pending
Compliance | TIN / Tax Registration | Yes | Annual | Provider Manager | Certificate | Valid | Provider Compliance Register | Pending
Insurance | Public Liability | Yes | Annual | Provider Manager | Certificate | Current and adequate | Provider Insurance Register | Pending
Technical | Electrical Competency | Yes | Annual | Operations | Certificate/training | Competent technicians | Provider Compliance Register | Pending
Technical | Refrigerant Handling | For gas jobs | Annual | Operations | Training evidence | Qualified technician | Provider Compliance Register | Pending
Safety | PPE Availability | Yes | Each job | Provider | Photo/confirmation | PPE available | Work Order Register | Pending
Delivery | Before & After Photos | Yes | Each job | Provider | Photos | Clear evidence | Project Register | Pending
Delivery | Completion Report | Yes | Each job | Provider | Report | Submitted before closure | Completion Register | Pending

## Client Master Register
Client ID | Project ID | Client Name | Client Type | Mobile | Email | Service Address | Property Type | Requested Service | Lead Source | Current Status | Assigned Consultant | Next Follow-Up | Notes
AC-C001 | AC-PRJ-0001 | Sample Client | Residential | 01XXXXXXXXX | client@example.com | Cumilla | House | Split AC Installation | Website | Lead | Sales Consultant |  | New enquiry
AC-C002 | AC-PRJ-0002 | Sample Business Client | Commercial | 01XXXXXXXXX | business@example.com | Cumilla | Restaurant | Emergency Repair | Referral | Assessment | Sales Consultant |  | Urgent repair

## Service Request Register
Request ID | Client ID | Project ID | Service Category | Specific Service | Priority | Requested Date | Preferred Date | Site Access Notes | Status | Assigned Provider | Remarks
AC-SR-0001 | AC-C001 | AC-PRJ-0001 | Installation | Wall Mounted Split AC | Normal |  |  | Access after 10am | Open | AC-P001 | Prepare quote
AC-SR-0002 | AC-C002 | AC-PRJ-0002 | Emergency | Cooling Problem / Fault Diagnosis | Urgent |  |  | Restaurant operating hours | Assessment | AC-P002 | Dispatch technician

## Site Assessment Register
Assessment ID | Project ID | Client ID | Property Type | Room Size | Existing Unit | Electrical Condition | Drainage Condition | Cooling Requirement | Risk Level | Recommendation | Assessment Photos | Assessed By | Assessment Date | Status
AC-SA-0001 | AC-PRJ-0001 | AC-C001 | House | Approx. 200 sqft | No | To be checked | To be checked | 1.5 Ton Split AC | Medium | Site visit required | Pending | AC-P001 |  | Planned
AC-SA-0002 | AC-PRJ-0002 | AC-C002 | Restaurant | Approx. 500 sqft | Yes | Existing issue | Drainage unknown | Repair / gas check | High | Urgent fault diagnosis | Pending | AC-P002 |  | Planned

## Quotation Register
Quote No | Project ID | Client ID | Service Type | Equipment Cost | Labour Cost | Transport Cost | Seventh Sky Fee | Other Cost | Total Quote | Quote Date | Validity | Client Decision | Approved Date | Notes
AC-Q-0001 | AC-PRJ-0001 | AC-C001 | Split AC Installation | BDT 90,000 | BDT 15,000 | BDT 5,000 | BDT 10,000 | BDT 0 | BDT 120,000 |  | 30 days | Pending
AC-Q-0002 | AC-PRJ-0002 | AC-C002 | Emergency Repair | BDT 3,000 | BDT 7,000 | BDT 2,000 | BDT 3,000 | BDT 0 | BDT 15,000 |  | 7 days | Pending

## Customer Agreement Register
Agreement ID | Project ID | Client ID | Agreement Type | Sent Date | Signed Date | Service Category | Project Value | Payment Terms | Status | Storage Link | Remarks
AC-AGR-0001 | AC-PRJ-0001 | AC-C001 | Customer Service Agreement |  |  | Installation | BDT 120,000 | 30/40/30 | Draft |  | Prepare after quote approval
AC-AGR-0002 | AC-PRJ-0002 | AC-C002 | Customer Service Agreement |  |  | Emergency Repair | BDT 15,000 | 100% on completion | Draft |  | Urgent

## Installation Project Register
Project ID | Client ID | AC Brand | Model | Capacity | No. Units | Installation Type | Provider ID | Start Date | Completion Date | Testing Done | Commissioning Done | Status | Warranty Expiry
AC-PRJ-0001 | AC-C001 |  |  | 1.5 Ton | 1 | Wall Mounted Split AC | AC-P001 |  |  | No | No | Not Started

## Maintenance Register
Maintenance ID | Project ID | Client ID | Service Type | Filter Cleaning | Coil Cleaning | Performance Check | Service Date | Next Due Date | Provider ID | Findings | Status
AC-MNT-0001 | AC-PRJ-0003 | AC-C003 | Quarterly Service | Yes | Yes | Yes |  |  | AC-P001 |  | Scheduled

## Repair Register
Repair ID | Project ID | Client ID | Fault Type | Diagnosis | Parts Required | Estimated Cost | Repair Action | Provider ID | Completion Date | Warranty | Status
AC-REP-0001 | AC-PRJ-0002 | AC-C002 | Cooling Problem | Pending diagnosis | Unknown | BDT ______ | Fault diagnosis first | AC-P002 |  | To be confirmed | Open

## Refrigerant Register
Gas Job ID | Project ID | Client ID | Gas Type | Leak Detection Done | Pressure Test Done | Gas Top-Up Amount | Technician | Date | Safety Notes | Status
AC-GAS-0001 | AC-PRJ-0002 | AC-C002 | R32 / R410A / Other | Pending | Pending |  | AC-P002 |  | Confirm gas type before work | Open

## AMC Register
AMC ID | Client ID | Project ID | Package | Frequency | Start Date | End Date | Last Service | Next Service | Assigned Provider | Renewal Reminder | Status
AC-AMC-0001 | AC-C001 | AC-PRJ-0001 | Residential Annual Plan | Annual |  |  |  |  | AC-P001 |  | Proposed
AC-AMC-0002 | AC-C002 | AC-PRJ-0002 | Restaurant AMC | Quarterly |  |  |  |  | AC-P002 |  | Proposed

## Warranty Register
Warranty ID | Project ID | Client ID | Warranty Type | Provider / Manufacturer | Start Date | Expiry Date | Coverage | Exclusions | Claim Process | Status
AC-WAR-0001 | AC-PRJ-0001 | AC-C001 | Installation Workmanship | AC-P001 |  |  | Installation defects only | Misuse/third-party repair excluded | Notify Seventh Sky in writing | Pending
AC-WAR-0002 | AC-PRJ-0002 | AC-C002 | Repair Labour | AC-P002 |  |  | Repair-specific only | New faults excluded | Inspection required | Pending

## Client Workflow Detailed
Phase | Step No | Workflow Step | Detailed Task / Activity | Responsible Person | CRM Record Required | Document / Evidence | Client Approval Required | Automation Opportunity | Output
Lead Management | 1 | Client Enquiry | Capture client details, address, property type and required AC service. | Sales Consultant | Client Master Register | Lead form | No | Auto-create Client ID and Project ID | Lead created
Needs Assessment | 2 | Service Selection | Identify whether service is consultation, installation, relocation, maintenance, repair, cleaning, gas, AMC, smart control or emergency. | Sales Consultant | Service Request Register | Needs checklist | Yes | Service category dropdown | Service scope identified
Site Assessment | 3 | Schedule Assessment | Assign provider/technician for site inspection or remote assessment. | Operations Coordinator | Site Assessment Register | Booking record | Yes | Auto-reminder to provider/client | Assessment booked
Site Assessment | 4 | Conduct Assessment | Review cooling requirement, room size, electrical condition, drainage and risk factors. | Provider | Site Assessment Register | Assessment report/photos | No | Mobile upload | Assessment completed
Proposal | 5 | Prepare Quotation | Prepare quotation showing equipment, labour, transport, Seventh Sky fee and optional insurance. | Sales / Accounts | Quotation Register | Quotation | Yes | Auto-populate quote from CRM | Quotation issued
Agreement | 6 | Sign Agreement | Send and collect customer service agreement before commencement. | Management | Agreement Register | Signed agreement | Yes | E-sign workflow | Agreement executed
Work Order | 7 | Assign Provider | Issue work order to approved provider with scope, cost, timeline and reporting requirements. | Operations Coordinator | Work Order Register | Work Order | No | Auto-populate work order | Provider assigned
Delivery | 8 | Service Delivery | Provider completes installation, repair, maintenance, cleaning, gas work or emergency service. | Provider | Project Register | Before/after photos | No | Status tracking | Service delivered
Quality | 9 | Testing & Handover | Complete testing, commissioning, report, warranty summary and client handover. | Provider/Coordinator | Completion Register | Completion report | Yes | Completion checklist | Client handover completed
Finance | 10 | Payment & Invoice | Issue invoice, record deposit/progress/final payment and provider payout. | Accounts | Invoice/Payment Register | Invoice/receipt | Yes | Payment reminders | Payment tracked
After-Sales | 11 | Warranty & AMC Setup | Register warranty, schedule AMC visits and set renewal reminders. | Coordinator | Warranty/AMC Register | Warranty record | No | Auto AMC reminders | After-sales support active
Closure | 12 | Feedback & Closure | Collect client feedback, close project and request referral/review. | Coordinator | Feedback Register | Survey | No | Auto feedback form | Project closed

## Client Checklist
Stage | Checklist Item | Required? | Responsible | Evidence Required | CRM Sheet | Status
Lead | Client name, mobile, address captured | Yes | Sales Consultant | CRM lead form | Client Master Register | Pending
Lead | Service category selected | Yes | Sales Consultant | Service selection | Service Request Register | Pending
Assessment | Site assessment scheduled | Yes | Coordinator | Booking note | Site Assessment Register | Pending
Assessment | Cooling requirement reviewed | Yes | Provider | Assessment report | Site Assessment Register | Pending
Assessment | Electrical condition checked | Yes | Provider | Assessment report/photos | Site Assessment Register | Pending
Proposal | Quotation issued | Yes | Sales/Accounts | Written quotation | Quotation Register | Pending
Agreement | Customer agreement signed | Yes | Management | Signed agreement | Agreement Register | Pending
Delivery | Work order issued | Yes | Operations | Work order | Work Order Register | Pending
Delivery | Before photos uploaded | Yes | Provider | Photos | Project Register | Pending
Delivery | Service completed | Yes | Provider | Completion report | Project Register | Pending
Quality | Testing/commissioning completed | If applicable | Provider | Testing report | Installation Register | Pending
Warranty | Warranty recorded | Yes | Coordinator | Warranty certificate | Warranty Register | Pending
Finance | Invoice issued and payment tracked | Yes | Accounts | Invoice/receipt | Invoice Register | Pending
Closure | Feedback collected | Yes | Coordinator | Feedback form | Feedback Register | Pending

## Invoice & Payment Register
Invoice No | Project ID | Client ID | Invoice Type | Invoice Amount | Due Date | Paid Amount | Outstanding | Payment Status | Provider Payout Status | Remarks
AC-INV-0001 | AC-PRJ-0001 | AC-C001 | Deposit | BDT 36,000 |  | BDT 0 | BDT 36,000 | Unpaid | Not Due | 30% deposit
AC-INV-0002 | AC-PRJ-0002 | AC-C002 | Emergency Repair | BDT 15,000 |  | BDT 0 | BDT 15,000 | Unpaid | Not Due | Pay after completion

## Complaint & Incident Register
Record ID | Type | Project ID | Client ID | Provider ID | Issue Description | Severity | Reported Date | Action Taken | Resolution Due | Status | Lessons Learned
AC-COMP-0001 | Complaint | AC-PRJ-0002 | AC-C002 | AC-P002 | Cooling not resolved after repair | Medium |  | Investigate provider report |  | Open
AC-INC-0001 | Safety Incident | AC-PRJ-0001 | AC-C001 | AC-P001 | Example: ladder safety concern | High |  | Stop work and investigate |  | Open

## KPI Dashboard Data
KPI | Target | Current | Data Source | Responsible | Review Frequency
Lead Response Time | Within 1 business day |  | Client Master Register | Sales Manager | Weekly
Site Assessment Completion | Within 3 business days |  | Site Assessment Register | Operations Manager | Weekly
Quotation Turnaround | Within 5 business days |  | Quotation Register | Sales Manager | Weekly
Service Completion Rate | > 95% |  | Project Register | Operations Manager | Monthly
Complaint Resolution | Within 5 business days |  | Complaint Register | Operations Manager | Monthly
AMC Renewal Rate | > 70% |  | AMC Register | Operations Manager | Monthly
Provider Compliance | 100% active providers compliant |  | Compliance Register | Provider Manager | Monthly
Cumilla Territory Compliance | 100% no breach |  | Cumilla Register | Director | Monthly