## Client Workflow Detailed
Phase | Step No | Task | Detailed Checklist | Responsible | Output
Lead Management | 1 | Receive Enquiry | Capture client details; identify service required; record lead source | BD Officer | Lead Record
Lead Management | 2 | Create Client File | Generate Client ID and Project ID; create CRM record | Coordinator | Client File
Consultation | 3 | Initial Consultation | Assess business structure and registration requirements | Coordinator | Consultation Notes
Consultation | 4 | Service Selection | Select trade licence and/or registration services | Coordinator | Service Checklist
Commercial | 5 | Issue Quotation | Prepare fees, govt charges and timeline | Admin | Quotation
Commercial | 6 | Execute Agreement | Obtain signed agreement and deposit | Admin | Agreement
Documents | 7 | Collect Documents | NID, passport, photos, address proof, shareholder/director docs | Coordinator | Document Register
Documents | 8 | Verify Documents | Check completeness and authenticity | Coordinator | Verification Checklist
Provider | 9 | Assign Provider | Select approved provider and issue work order | Operations | Assignment
Delivery | 10 | Name Clearance | Prepare and submit name clearance | Provider | Name Clearance
Delivery | 11 | Trade Licence Support | Prepare trade licence package | Provider | Licence Package
Delivery | 12 | Business Registration | Prepare RJSC/company formation docs | Provider | Registration Package
Delivery | 13 | Authority Liaison | Follow up with authorities | Coordinator | Progress Update
QA | 14 | Review Deliverables | Check accuracy and compliance | Operations | QA Record
Completion | 15 | Issue Final Documents | Deliver registration outputs | Coordinator | Completion Pack
Completion | 16 | Final Invoice & Closure | Collect final payment and archive file | Finance | Closed Project

## Client Checklist
Category | Checklist Item | Completed
Client | Signed Agreement
Client | Deposit Received
Documents | NID Copy
Documents | Passport Copy
Documents | Address Evidence
Business | Business Name Confirmed
Business | Shareholder Details Received
Business | Director Details Received
Completion | Final Documents Delivered
Completion | Final Payment Received

## Provider Workflow
Phase | Step No | Task | Detailed Checklist | Responsible | Output
Onboarding | 1 | Collect Credentials | Licence, registration, certifications, references | Vendor Manager | Provider File
Onboarding | 2 | Execute MSPA | Sign MSPA and confidentiality obligations | Vendor Manager | MSPA
Onboarding | 3 | Approve Provider | Allocate Provider ID | Vendor Manager | Approved Provider
Assignment | 4 | Receive Work Order | Review scope and timeline | Provider | Accepted WO
Delivery | 5 | Review Documents | Review client documentation | Provider | Review Notes
Delivery | 6 | Prepare Documents | Prepare registration forms and supporting docs | Provider | Document Package
Delivery | 7 | Registration Coordination | Coordinate submissions | Provider | Submission Record
Delivery | 8 | Progress Reporting | Provide weekly updates | Provider | Status Report
QA | 9 | Submit Deliverables | Submit to Seventh Sky | Provider | Deliverables
QA | 10 | Rectify Issues | Address comments | Provider | Revised Deliverables
Commercial | 11 | Submit Invoice | Invoice per work order | Provider | Invoice
Commercial | 12 | Receive Payment | Payment after approval | Finance | Payment Record

## Provider Checklist
Category | Checklist Item | Completed
Onboarding | Trade Licence Verified
Onboarding | Company Registration Verified
Onboarding | MSPA Signed
Onboarding | Insurance Verified
Assignment | Work Order Accepted
Delivery | Documents Reviewed
Delivery | Registration Submitted
Delivery | Progress Reports Submitted
QA | Deliverables Approved
Commercial | Invoice Submitted
Commercial | Payment Released