## End User Workflow
Workflow Stage | Task / Activity | Responsible Team | Payment Workflow | Required Documents | CRM / System Update | Status | Remarks
Lead Intake | Receive commercial client enquiry and register CRM profile | Client Relations Team | No payment at this stage | Client Intake Form | Lead Register
Consultation | Conduct commercial design consultation | Commercial Design Coordination | Collect consultation fee if applicable | Consultation Notes | Consultation Tracker
Commercial Site Assessment | Conduct site inspection and operational assessment | Operations Team | Collect assessment fee | Inspection Report | Inspection Register
Quotation & Proposal | Prepare quotation and project scope | Finance & Coordination Team | Issue project quotation and stage payment structure | Quotation | Quotation Register
Agreement Execution | Execute commercial interior design agreement | Documentation Team | Collect initial deposit | Signed Agreement | Agreement Register
Design Development | Prepare commercial concepts and layouts | Interior Design Team | Collect Stage 2 payment | Concept Designs | Design Workflow
Execution Coordination | Coordinate fit-out and renovation work | Project Coordinator | Collect Stage 3 execution payment | Execution Checklist | Execution Tracker
Vendor Payment Approval | Approve subcontractor milestone completion | Project Coordinator & Finance | Verify subcontractor invoice | Progress Report | Vendor Payment Register
Variation Management | Coordinate additional work and revisions | Project Coordinator | Collect approved variation charges before execution | Variation Form | Variation Register
Final Completion | Coordinate final inspection and styling | Quality Control Team | Collect final outstanding balance | QC Checklist | Completion Register
Subcontractor Final Settlement | Release final subcontractor payment | Finance Team | Disburse final vendor payment after sign-off | Payment Record | Finance Register
Project Handover | Complete project handover | Operations Team | Confirm all dues cleared | Handover Report | Handover Register

## End User Enterprise WF
Department | Enterprise Workflow Process | Key Actions | Payment Control | Required Evidence | Reporting Requirement | Escalation Trigger
Client Relations | Lead Intake & Consultation | Register commercial client and requirements | Consultation fee verification | Client Intake Form | CRM Update | Fake client details
Operations | Commercial Site Assessment | Conduct inspection and operational review | Assessment fee confirmation | Inspection Report | Site Assessment Report | Unsafe property condition
Finance | Quotation & Deposit | Issue quotation and collect project deposit | Deposit verification | Quotation & Receipt | Finance Update | Payment default
Commercial Design Team | Design Development | Coordinate commercial design workflow | Stage 2 payment verification | Concept Plans | Design Report | Unapproved variation
Project Coordination | Execution Coordination | Coordinate fit-out and renovation | Execution payment tracking | Execution Reports | Execution Update | Project delay
Finance | Vendor Payment Verification | Verify subcontractor invoice and milestone | Milestone verification | Vendor Invoice | Finance Register | Invoice mismatch
Project Coordination | Variation Management | Approve project variations | Variation charge approval | Variation Form | Variation Report | Unauthorised variation
Quality Control | Final Inspection | Conduct commercial quality review | Final balance clearance | QC Checklist | QC Report | Major defect
Finance | Final Settlement | Release final subcontractor payment | Final reconciliation | Settlement Record | Settlement Report | Outstanding dues
Operations | Project Handover | Coordinate final handover and closure | Payment completion confirmation | Handover Report | Closure Report | Client dispute

## Vendor Workflow
Workflow Stage | Task / Activity | Responsible Party | Payment Workflow | Required Documents | CRM / System Update | Status | Remarks
Vendor Registration | Register approved commercial interior designer/vendor | Vendor Management Team | No payment | Vendor Agreement | Vendor Register
Project Allocation | Assign commercial project to subcontractor | Project Coordinator | Issue approved work order | Project Allocation Form | Vendor Tracker
Concept Planning | Coordinate commercial design planning | Interior Designer | No direct client payment allowed | Concept Notes | Project Workflow
Quotation Submission | Submit subcontractor quotation to Seventh Sky | Interior Designer | Vendor submits quotation internally only | Vendor Quotation | Quotation Register
Execution Commencement | Commence approved execution work | Interior Designer | Stage-based payment eligibility begins | Execution Checklist | Execution Tracker
Progress Reporting | Provide project progress updates | Interior Designer | Invoice subject to milestone approval | Progress Reports | Project Monitoring
Invoice Submission | Submit invoice to Seventh Sky | Interior Designer | No direct client invoicing permitted | Vendor Invoice | Finance Register
Payment Verification | Verify milestone completion | Finance & Operations | Approve subcontractor payment | Inspection Report | Payment Approval Log
Vendor Payment | Disburse approved payment to vendor | Finance Team | Transfer payment to vendor account | Payment Record | Finance Register
Final Completion | Complete commercial project closure | Interior Designer | Final settlement after client sign-off | Completion Record | Closure Register

## Vendor Enterprise WF
Department | Enterprise Workflow Process | Key Actions | Payment Control | Required Evidence | Reporting Requirement | Escalation Trigger
Vendor Management | Vendor Registration & Approval | Approve subcontractor onboarding | Verify vendor bank details | Vendor Agreement | Vendor Register | Unverified vendor
Project Coordination | Project Allocation | Assign commercial project and issue work order | Internal costing review | Project Allocation Form | Allocation Report | Pricing conflict
Commercial Design Coordination | Concept Development | Coordinate commercial concept planning | No direct client payment permitted | Concept Notes | Design Workflow | Direct client communication
Finance | Quotation Review | Review subcontractor quotation | Margin and pricing review | Vendor Quotation | Finance Update | Pricing inconsistency
Operations | Execution Monitoring | Monitor project execution workflow | Milestone verification | Execution Reports | Execution Report | Poor workmanship
Finance | Invoice Verification | Verify milestone invoice | Cross-check against project progress | Vendor Invoice | Finance Register | Unapproved invoice
Finance | Vendor Payment Disbursement | Release approved vendor payment | Payment authorisation required | Payment Record | Payment Report | Payment dispute
Compliance | Non-Circumvention Monitoring | Monitor bypass or direct dealing | Commission protection review | Communication Records | Compliance Report | Direct client bypass
Operations | Project Completion | Conduct final inspection and sign-off | Final settlement reconciliation | Completion Checklist | Closure Report | Outstanding defect