SEVENTH SKY PROPERTY CARE

COMMERCIAL INTERIOR DESIGN SOLUTIONS

STANDARD OPERATING PROCEDURE (SOP)

CLIENT / END USER MANAGEMENT

Document No: SSPC-CIDS-SOP-01
Version: 0.1
Effective Date: __________
Division: Seventh Sky Interior Design Solutions

Table of Contents

SOP - COMMERCIAL INTERIOR DESIGN SOLUTIONS – END USER / CLIENT MANAGEMENT	3

1. PURPOSE	3

2. SCOPE	3

3. KEY OBJECTIVES	4

4. CLIENT ONBOARDING PROCEDURE	4

Step 1 – Lead Intake	4

Step 2 – Consultation & Requirement Analysis	4

Step 3 – Preliminary Feasibility Review	5

5. COMMERCIAL PROPERTY ASSESSMENT PROCEDURE	5

6. CLIENT AGREEMENT PROCEDURE	5

7. PROJECT WORKFLOW STRUCTURE	6

PHASE 1 – CONSULTATION & COMMERCIAL DESIGN ASSESSMENT	6

PHASE 2 – DESIGN DEVELOPMENT	6

PHASE 3 – EXECUTION & PROJECT COORDINATION	7

PHASE 4 – FINAL COMPLETION & HANDOVER	8

8. SUBCONTRACTOR MANAGEMENT PROCEDURE	8

9. NON-CIRCUMVENTION & CLIENT PROTECTION PROCEDURE	9

10. CLIENT PAYMENT & FINANCIAL CONTROL PROCEDURE	10

11. SUBCONTRACTOR PAYMENT DISBURSEMENT PROCEDURE	11

12. VARIATION MANAGEMENT PROCEDURE	11

13. QUALITY CONTROL PROCEDURE	11

14. CLIENT COMMUNICATION PROCEDURE	12

15. DAMAGE, INCIDENT & ESCALATION PROCEDURE	12

16. DISPUTE MANAGEMENT PROCEDURE	12

17. RECORD RETENTION PROCEDURE	13

18. TERMINATION PROCEDURE	13

# SOP - COMMERCIAL INTERIOR DESIGN SOLUTIONS – END USER / CLIENT MANAGEMENT

# 1. PURPOSE

This Standard Operating Procedure (SOP) establishes the operational workflow, customer management framework, payment collection process, commercial project coordination workflow, subcontractor coordination standards, documentation procedures, and risk management process for Commercial Interior Design Services provided by Seventh Sky Property Care to end user clients.

This SOP aims to ensure:

- structured commercial project delivery,

- operational transparency,

- timely payment collection,

- subcontractor control,

- professional communication,

- project quality management,

- and protection of Seventh Sky commercial interests.

# 2. SCOPE

This SOP applies to all Seventh Sky:

- employees,

- consultants,

- project coordinators,

- finance personnel,

- operations personnel,

- subcontractors,

- and authorised representatives

involved in:

- commercial interior design,

- office fit-out,

- retail setup,

- restaurant & café setup,

- showroom setup,

- renovation coordination,

- and project supervision.

# 3. KEY OBJECTIVES

The objectives of this SOP are to:

- Maintain structured project workflow.

- Ensure professional client management.

- Ensure proper payment collection.

- Prevent client bypass of subcontractors.

- Ensure project documentation and approvals.

- Maintain quality control standards.

- Minimise operational, financial, and legal risks.

- Protect Seventh Sky commercial arrangements.

# 4. CLIENT ONBOARDING PROCEDURE

## Step 1 – Lead Intake

The assigned officer shall:

- create CRM profile,

- assign project reference number,

- collect business details,

- collect property details,

- and schedule consultation.

## Step 2 – Consultation & Requirement Analysis

The consultation shall generally cover:

- business operational requirements,

- branding requirements,

- commercial layout expectations,

- renovation scope,

- furnishing requirements,

- project budget,

- and timeline expectations.

## Step 3 – Preliminary Feasibility Review

The assigned coordinator shall review:

- operational feasibility,

- budget feasibility,

- timeline practicality,

- property suitability,

- and project risk factors.

High-risk or complex projects shall be escalated to management.

# 5. COMMERCIAL PROPERTY ASSESSMENT PROCEDURE

The assigned team shall coordinate:

- commercial site inspection,

- measurements,

- photography,

- operational assessment,

- and renovation feasibility review.

Assessment findings should generally be documented in CRM.

# 6. CLIENT AGREEMENT PROCEDURE

Before project commencement:

- Commercial Interior Design Agreement must be signed.

- Scope of work must be confirmed.

- Payment structure must be approved.

- Project stages must be documented.

- Variation process must be clarified.

No project shall commence without:

- signed agreement,

- initial payment confirmation,

- and operational approval where required.

# 7. PROJECT WORKFLOW STRUCTURE

## PHASE 1 – CONSULTATION & COMMERCIAL DESIGN ASSESSMENT

This phase may include:

- consultation,

- commercial site visit,

- measurements,

- operational assessment,

- preliminary concept discussion,

- and feasibility analysis.

Phase 1 Payment Collection

The Finance Team shall collect:

- consultation fee,

- site assessment fee,

- concept planning fee,

- or commercial design assessment fee
before or during this phase.

Phase 1 fees are generally non-refundable once services commence.

## PHASE 2 – DESIGN DEVELOPMENT

This phase may include:

- commercial layout planning,

- 2D / 3D concept development,

- branding integration,

- furnishing planning,

- lighting concepts,

- and quotation preparation.

Client Approval Requirement

The Client should generally approve:

- layouts,

- concepts,

- materials,

- quotations,

- estimated pricing,

- and project scope
before execution begins.

Phase 2 Payment Collection

The Finance Team shall collect:

- design development payment,

- advance project deposit,

- or agreed stage payment
before releasing finalised concepts for execution.

## PHASE 3 – EXECUTION & PROJECT COORDINATION

This phase may include:

- fit-out coordination,

- renovation coordination,

- subcontractor coordination,

- labour coordination,

- material coordination,

- and project supervision.

Execution Payment Workflow

The Client shall generally pay:

- stage-based execution payment,

- material advance,

- labour advance,

- or milestone payment
before corresponding execution stage commences.

Payment Verification Procedure

The Finance Team shall:

- verify payment,

- issue receipt,

- update CRM,

- and notify Project Coordinator before work continuation.

## PHASE 4 – FINAL COMPLETION & HANDOVER

This phase may include:

- final installation,

- finishing work,

- styling coordination,

- defect review,

- inspection,

- and handover.

Final Payment Procedure

Before project handover:

- all outstanding dues should generally be cleared,

- variation charges reconciled,

- and final invoice settled.

# 8. SUBCONTRACTOR MANAGEMENT PROCEDURE

Seventh Sky may engage:

- commercial interior designers,

- labour contractors,

- suppliers,

- electricians,

- carpenters,

- painters,

- HVAC technicians,

- and specialist service providers.

All subcontractor communication should generally remain coordinated through Seventh Sky.

# 9. NON-CIRCUMVENTION & CLIENT PROTECTION PROCEDURE

Protected Vendor Relationship

Any:

- interior designer,

- subcontractor,

- supplier,

- contractor,

- labour provider,

- consultant,

- or vendor
introduced through Seventh Sky shall remain protected operational relationship of Seventh Sky.

Restriction Period

The Client must not:

- directly hire,

- privately engage,

- privately negotiate,

- privately continue work,

- or bypass Seventh Sky
with introduced subcontractors during:

- active project period; and

- Twelve (12) months after project completion.

Circumvention Monitoring

The assigned coordinator shall monitor:

- unusual direct communication,

- hidden meetings,

- private quotation requests,

- and bypass behaviour.

# 10. CLIENT PAYMENT & FINANCIAL CONTROL PROCEDURE

Payment Collection Principle

All client payments shall generally be made to:

Seventh Sky Property Care ONLY

Clients should not directly pay subcontractors unless formally approved.

Payment Methods

Accepted payment methods may include:

- bank transfer,

- cheque,

- online transfer,

- approved payment gateway,

- or other approved methods.

Finance Workflow

The Finance Team shall:

- issue invoices,

- issue receipts,

- track payment stages,

- maintain financial records,

- reconcile project accounts,

- and authorise subcontractor disbursement.

# 11. SUBCONTRACTOR PAYMENT DISBURSEMENT PROCEDURE

Subcontractor payments shall generally:

- remain milestone-based,

- require progress verification,

- require operational approval,

- and require Finance Team authorisation.

No subcontractor payment should generally be released without:

- verified work completion,

- invoice submission,

- and Project Coordinator approval.

# 12. VARIATION MANAGEMENT PROCEDURE

Any:

- design variation,

- material change,

- layout revision,

- timeline extension,

- or budget adjustment
must generally be:

- documented,

- approved,

- and financially reconciled
before implementation.

# 13. QUALITY CONTROL PROCEDURE

The assigned coordinator shall monitor:

- workmanship quality,

- installation quality,

- project cleanliness,

- material consistency,

- and project completion standards.

Where defects identified:

- corrective action should be coordinated,

- subcontractor notified,

- and records maintained.

# 14. CLIENT COMMUNICATION PROCEDURE

All major:

- approvals,

- quotations,

- variation discussions,

- pricing discussions,

- and project updates
should generally:

- remain documented,

- be updated in CRM,

- and follow approved communication channels.

# 15. DAMAGE, INCIDENT & ESCALATION PROCEDURE

If damage or operational issue occurs:

- Record incident immediately.

- Notify management.

- Collect photo/video evidence.

- Notify responsible subcontractor.

- Coordinate corrective action where applicable.

# 16. DISPUTE MANAGEMENT PROCEDURE

If disputes arise:

- Record issue immediately.

- Preserve communication records.

- Attempt amicable resolution.

- Escalate unresolved matters to management.

- Refer legal matters where required.

# 17. RECORD RETENTION PROCEDURE

Maintain:

- agreements,

- invoices,

- quotations,

- variation approvals,

- payment records,

- communication logs,

- inspection reports,

- and project reports.

Recommended retention:

- Minimum Seven (7) Years.

# 18. TERMINATION PROCEDURE

Services may be terminated where:

- payments overdue,

- fraud identified,

- repeated operational disruption occurs,

- unlawful conduct identified,

- or material breach occurs.

Non-circumvention obligations survive termination.

Approved By

Managing Director
Seventh Sky Property Care

Name: __________________________

Signature: ______________________

Date: ____ / ____ / ______