SEVENTH SKY PROPERTY CARE

FITNESS ROOM INTERIOR DESIGN SOLUTIONS

STANDARD OPERATING PROCEDURE (SOP)

CLIENT / END USER MANAGEMENT

Document No: SSPC-FRIDS - SOP-01
Version: 0.1
Effective Date: __________
Division: Seventh Sky Interior Design Solutions

Table of Contents

SOP- FITNESS ROOM INTERIOR DESIGN SOLUTIONS (CLIENT / END USER MANAGEMENT)	3

1. PURPOSE	3

2. SCOPE	3

3. KEY OBJECTIVES	4

4. CLIENT ONBOARDING PROCEDURE	4

Step 1 – Lead Intake	4

Step 2 – Consultation & Requirement Analysis	4

Step 3 – Preliminary Feasibility Review	5

5. FITNESS ROOM PROPERTY ASSESSMENT PROCEDURE	5

6. CLIENT AGREEMENT PROCEDURE	5

7. PROJECT WORKFLOW STRUCTURE	6

PHASE 1 – CONSULTATION & FITNESS ROOM DESIGN ASSESSMENT	6

PHASE 2 – DESIGN DEVELOPMENT	6

PHASE 3 – EXECUTION & PROJECT COORDINATION	7

PHASE 4 – FINAL COMPLETION & HANDOVER	8

8. SUBCONTRACTOR MANAGEMENT PROCEDURE	8

9. NON-CIRCUMVENTION & CLIENT PROTECTION PROCEDURE	9

10. CLIENT PAYMENT & FINANCIAL CONTROL PROCEDURE	10

11. SUBCONTRACTOR PAYMENT DISBURSEMENT PROCEDURE	10

12. VARIATION MANAGEMENT PROCEDURE	10

13. QUALITY CONTROL PROCEDURE	11

14. CLIENT COMMUNICATION PROCEDURE	11

15. DAMAGE, INCIDENT & ESCALATION PROCEDURE	12

16. DISPUTE MANAGEMENT PROCEDURE	12

17. RECORD RETENTION PROCEDURE	12

18. TERMINATION PROCEDURE	13

SOP- FITNESS ROOM INTERIOR DESIGN SOLUTIONS (CLIENT / END USER MANAGEMENT)

# 1. PURPOSE

This Standard Operating Procedure (SOP) establishes the operational workflow, customer management framework, payment collection process, project coordination workflow, subcontractor coordination standards, documentation procedures, and risk management process for Fitness Room Interior Design Services provided by Seventh Sky Property Care to end user clients.

This SOP aims to ensure:

- structured project delivery;

- operational transparency;

- timely payment collection;

- subcontractor control;

- professional communication;

- project quality management; and

- protection of Seventh Sky commercial interests.

# 2. SCOPE

This SOP applies to all Seventh Sky:

- employees;

- consultants;

- project coordinators;

- finance personnel;

- operations personnel;

- subcontractors; and

- authorised representatives

involved in:

- fitness room interior design;

- gym fit-out;

- fitness space planning;

- home gym setup;

- commercial gym setup;

- corporate fitness centre setup;

- wellness studio setup;

- renovation coordination; and

- project supervision.

# 3. KEY OBJECTIVES

The objectives of this SOP are to:

- Maintain structured project workflow.

- Ensure professional client management.

- Ensure proper payment collection.

- Prevent client bypass of subcontractors.

- Ensure project documentation and approvals.

- Maintain quality control standards.

- Minimise operational, financial and legal risks.

- Protect Seventh Sky commercial arrangements.

# 4. CLIENT ONBOARDING PROCEDURE

## Step 1 – Lead Intake

The assigned officer shall:

- create CRM profile;

- assign project reference number;

- collect client details;

- collect property details; and

- schedule consultation.

## Step 2 – Consultation & Requirement Analysis

The consultation shall generally cover:

- fitness room requirements;

- property requirements;

- equipment requirements;

- renovation scope;

- furnishing requirements;

- project budget; and

- timeline expectations.

## Step 3 – Preliminary Feasibility Review

The assigned coordinator shall review:

- operational feasibility;

- budget feasibility;

- timeline practicality;

- property suitability; and

- project risk factors.

High-risk or complex projects shall be escalated to management.

# 5. FITNESS ROOM PROPERTY ASSESSMENT PROCEDURE

The assigned team shall coordinate:

- fitness room site inspection;

- measurements;

- photography;

- operational assessment; and

- renovation feasibility review.

Assessment findings should generally be documented in the CRM.

# 6. CLIENT AGREEMENT PROCEDURE

Before project commencement:

- Fitness Room Interior Design Solutions Customer Service Agreement must be signed.

- Scope of work must be confirmed.

- Payment structure must be approved.

- Project stages must be documented.

- Variation process must be clarified.

No project shall commence without:

- signed agreement;

- initial payment confirmation; and

- operational approval where required.

# 7. PROJECT WORKFLOW STRUCTURE

## PHASE 1 – CONSULTATION & FITNESS ROOM DESIGN ASSESSMENT

This phase may include:

- consultation;

- fitness room site visit;

- measurements;

- operational assessment;

- preliminary concept discussion; and

- feasibility analysis.

Phase 1 Payment Collection

The Finance Team shall collect:

- consultation fee;

- site assessment fee;

- concept planning fee; or

- fitness room design assessment fee

before or during this phase.

Phase 1 fees are generally non-refundable once services commence.

## PHASE 2 – DESIGN DEVELOPMENT

This phase may include:

- fitness room layout planning;

- 2D / 3D concept development;

- equipment layout planning;

- furnishing planning;

- lighting concepts; and

- quotation preparation.

Client Approval Requirement

The Client should generally approve:

- layouts;

- concepts;

- materials;

- quotations;

- estimated pricing; and

- project scope

before execution begins.

Phase 2 Payment Collection

The Finance Team shall collect:

- design development payment;

- advance project deposit; or

- agreed stage payment

before releasing finalised concepts for execution.

## PHASE 3 – EXECUTION & PROJECT COORDINATION

This phase may include:

- fitness room fit-out coordination;

- renovation coordination;

- subcontractor coordination;

- labour coordination;

- material coordination; and

- project supervision.

Execution Payment Workflow

The Client shall generally pay:

- stage-based execution payment;

- material advance;

- labour advance; or

- milestone payment

before the corresponding execution stage commences.

Payment Verification Procedure

The Finance Team shall:

- verify payment;

- issue receipt;

- update CRM; and

- notify the Project Coordinator before work continuation.

## PHASE 4 – FINAL COMPLETION & HANDOVER

This phase may include:

- final installation;

- finishing work;

- equipment placement coordination;

- defect review;

- inspection; and

- handover.

Final Payment Procedure

Before project handover:

- all outstanding dues should generally be cleared;

- variation charges reconciled; and

- final invoice settled.

# 8. SUBCONTRACTOR MANAGEMENT PROCEDURE

Seventh Sky may engage:

- fitness room interior designers;

- labour contractors;

- suppliers;

- electricians;

- carpenters;

- painters;

- equipment installers; and

- specialist service providers.

All subcontractor communication should generally remain coordinated through Seventh Sky.

# 9. NON-CIRCUMVENTION & CLIENT PROTECTION PROCEDURE

Protected Vendor Relationship

Any:

- interior designer;

- subcontractor;

- supplier;

- contractor;

- labour provider;

- consultant; or

- vendor

introduced through Seventh Sky shall remain a protected operational relationship of Seventh Sky.

Restriction Period

The Client must not:

- directly hire;

- privately engage;

- privately negotiate;

- privately continue work; or

- bypass Seventh Sky

with introduced subcontractors during:

- the active project period; and

- twelve (12) months after project completion.

Circumvention Monitoring

The assigned Project Coordinator shall monitor:

- unusual direct communication;

- hidden meetings;

- private quotation requests; and

- bypass behaviour.

# 10. CLIENT PAYMENT & FINANCIAL CONTROL PROCEDURE

Payment Collection Principle

All client payments shall generally be made to:

Seventh Sky Property Care ONLY

Clients should not directly pay subcontractors unless formally approved.

Payment Methods

Accepted payment methods may include:

- bank transfer;

- cheque;

- online transfer; or

- other approved payment methods.

Payment Verification

The Finance Team shall:

- verify payment receipt;

- issue receipt;

- update CRM records; and

- notify the Project Coordinator.

# 11. SUBCONTRACTOR PAYMENT DISBURSEMENT PROCEDURE

Before subcontractor payment is released, the Finance Team shall generally verify:

- completed work;

- Project Coordinator approval;

- agreed subcontractor invoice; and

- supporting documentation.

Approved payments shall generally be processed in accordance with Seventh Sky's financial procedures.

# 12. VARIATION MANAGEMENT PROCEDURE

Where the Client requests changes to:

- project scope;

- layout;

- materials;

- equipment layout;

- furnishings; or

- other agreed services,

the Project Coordinator shall generally:

- assess the requested variation;

- obtain revised quotations where required;

- obtain Client approval;

- update project documentation; and

- notify relevant subcontractors before implementation.

No variation work should generally commence until the required approvals have been obtained.

# 13. QUALITY CONTROL PROCEDURE

Throughout the project, the Project Coordinator shall generally monitor:

- workmanship quality;

- approved design compliance;

- material quality;

- project progress;

- subcontractor performance; and

- overall client satisfaction.

Where defects or non-conformities are identified, appropriate corrective action shall be coordinated before project completion.

# 14. CLIENT COMMUNICATION PROCEDURE

Throughout the project, the assigned Project Coordinator shall generally:

- maintain regular communication with the Client;

- provide project progress updates;

- respond to Client enquiries;

- coordinate project meetings where required;

- communicate approved variations; and

- provide handover information.

All significant project communications should generally be documented within the CRM or Project File.

# 15. DAMAGE, INCIDENT & ESCALATION PROCEDURE

Where property damage, safety incidents or significant project issues occur, the Project Coordinator shall generally:

- assess the situation;

- notify the Client where appropriate;

- document the incident;

- coordinate corrective action; and

- notify management where required.

Where third-party contractors or suppliers are involved, Seventh Sky shall coordinate communication with the relevant parties.

# 16. DISPUTE MANAGEMENT PROCEDURE

Where a dispute arises during the project:

- The Project Coordinator shall first attempt to resolve the matter through discussion with the Client.

- Where the matter cannot be resolved, it shall be escalated to management.

- Where appropriate, supporting project documentation shall be reviewed.

- If the dispute remains unresolved, the Parties may proceed in accordance with the dispute resolution provisions contained within the Fitness Room Interior Design Solutions – Customer Service Agreement.

# 17. RECORD RETENTION PROCEDURE

The following records should generally be retained:

- Client enquiry records;

- signed Customer Service Agreement;

- quotations;

- payment records;

- project documentation;

- approved variations; and

- project correspondence.

Records should generally be maintained within the CRM and Project File in accordance with Seventh Sky's document management procedures.

# 18. TERMINATION PROCEDURE

Where a project is terminated before completion, the Project Coordinator shall generally:

- record the reason for termination;

- update the Project File;

- notify relevant parties;

- reconcile outstanding payments where applicable; and

- close the project following management approval.

Any outstanding financial matters shall be managed in accordance with the Fitness Room Interior Design Solutions – Customer Service Agreement and Seventh Sky's financial procedures.

Approved By

Managing Director
Seventh Sky Property Care

Name: __________________________

Signature: ______________________

Date: ____ / ____ / ______

END OF SOP