## Client Workflow
Phase | Step | Activity | Checklist | Responsible | Status
Lead | 1 | Receive enquiry | Lead recorded | Business Development
Lead | 2 | Qualify client | Budget and property confirmed | Business Development
Consultation | 3 | Consultation meeting | Requirements captured | Project Coordinator
Assessment | 4 | Site inspection | Measurements/photos/Qibla assessed | Project Coordinator
Commercial | 5 | Issue agreement | Agreement sent | Admin
Commercial | 6 | Collect deposit | Deposit received | Finance
Design | 7 | Issue design brief | Brief sent to designer | Project Coordinator
Design | 8 | Present design | Feedback obtained | Project Coordinator
Design | 9 | Final approval | Written approval received | Client
Procurement | 10 | Obtain quotes | Quotes reviewed | Procurement
Implementation | 11 | Coordinate works | Progress monitored | Project Coordinator
QC | 12 | Inspection | Defects checked | Operations
Handover | 13 | Collect final payment | Payment received | Finance
Handover | 14 | Close project | Completion report issued | Project Coordinator

## Client Checklist
Item | Completed
Consultation completed
Site inspection completed
Agreement signed
Deposit received
Design approved
Quotes approved
Works completed
Final inspection completed
Final payment received
Completion report issued

## Designer Workflow
Phase | Step | Activity | Checklist | Responsible | Status
Onboarding | 1 | Verify credentials | Licence and portfolio verified | Vendor Manager
Onboarding | 2 | Sign PSPA | Agreement executed | Vendor Manager
Allocation | 3 | Issue work order | Scope issued | Project Coordinator
Design | 4 | Prepare concept | Concept submitted | Designer
Design | 5 | Revisions | Feedback addressed | Designer
Design | 6 | Final submission | Final package delivered | Designer
Support | 7 | Clarifications | Responses provided | Designer
QC | 8 | Rectifications | Issues resolved | Designer
Payment | 9 | Submit invoice | Invoice lodged | Designer
Payment | 10 | Receive payment | Deliverables verified | Finance
Review | 11 | Performance review | Scorecard completed | Vendor Manager

## Designer Checklist
Item | Completed
PSPA signed
Insurance verified
Work order accepted
Concept submitted
Revisions completed
Final design submitted
Invoice submitted
Payment received
Performance review completed