## End User Workflow
Workflow Stage | Task / Activity | Responsible Team | Payment Workflow | Required Documents | CRM / System Update | Status | Remarks
Lead Intake | Receive client enquiry and create CRM profile | Client Relations | No payment at this stage | Client Intake Form | Lead Register
Consultation | Conduct consultation and requirement analysis | Interior Design Coordination | Collect consultation fee if applicable | Consultation Notes | Consultation Tracker
Site Assessment | Conduct property inspection and measurements | Operations Team | Collect site visit / assessment fee | Inspection Report | Inspection Register
Quotation | Prepare quotation and project costing | Finance & Coordination | Issue quotation and stage-based payment schedule | Quotation | Quotation Register
Agreement | Execute service agreement | Documentation Team | Collect initial project deposit | Signed Agreement | Agreement Register
Design Development | Prepare concepts and layouts | Interior Designer | Collect Stage 2 payment from client | Design Concepts | Design Workflow
Execution Coordination | Coordinate renovation and fit-out | Project Coordinator | Collect Stage 3 execution payment | Execution Checklist | Execution Tracker
Subcontractor Payment | Disburse approved subcontractor payment | Finance Team | Pay approved subcontractor invoice after verification | Vendor Invoice | Finance Register
Variation Management | Manage project variations | Project Coordinator | Collect variation charges before execution | Variation Form | Variation Register
Final Styling | Coordinate final styling and completion | Interior Design Team | Collect final outstanding balance | Completion Checklist | Completion Tracker
Final Disbursement | Release final subcontractor payment | Finance Team | Final subcontractor settlement after project sign-off | Payment Record | Finance Register
Handover | Project handover to client | Operations Team | Confirm all dues cleared | Handover Report | Handover Register

## End User Enterprise WF
Department | Enterprise Workflow Process | Key Actions | Payment Control | Required Evidence | Reporting Requirement | Escalation Trigger
Client Relations | Lead Intake & Consultation | Register client and schedule consultation | Consultation fee collection | Client Intake Form | CRM Update | Fake client details
Operations | Property Assessment | Conduct site assessment | Assessment fee verification | Inspection Report | Assessment Report | Unsafe property condition
Finance | Quotation & Deposit | Issue quotation and collect deposit | Deposit verification | Quotation & Receipt | Finance Update | Payment default
Interior Design Coordination | Design Development | Coordinate design workflow | Stage 2 payment confirmation | Design Concepts | Design Report | Unapproved design variation
Project Coordination | Execution Coordination | Coordinate labour and renovation | Execution payment tracking | Execution Records | Execution Report | Project delay
Finance | Subcontractor Payment | Disburse subcontractor payment | Invoice verification | Vendor Invoice | Finance Register | Unverified invoice
Project Coordination | Variation Management | Approve and execute variations | Variation charge approval | Variation Form | Variation Report | Unauthorised variation
Quality Control | Final Inspection | Inspect workmanship quality | Final payment clearance | QC Checklist | QC Report | Major defect
Finance | Final Settlement | Release final subcontractor payment | Final settlement reconciliation | Settlement Record | Settlement Report | Outstanding dues
Operations | Project Handover | Complete handover and closure | Confirm all payments cleared | Handover Report | Closure Report | Client dispute

## Vendor Workflow
Workflow Stage | Task / Activity | Responsible Party | Payment Workflow | Required Documents | CRM / System Update | Status | Remarks
Vendor Onboarding | Register approved interior designer/vendor | Vendor Management Team | No payment | Vendor Agreement | Vendor Register
Project Allocation | Assign project to subcontractor | Project Coordinator | Issue project work order | Project Allocation Form | Vendor Tracker
Design Consultation | Coordinate design planning | Interior Designer | No direct client payment allowed | Concept Notes | Project Workflow
Quotation Submission | Submit internal costing to Seventh Sky | Interior Designer | Vendor submits quotation to Seventh Sky only | Vendor Quotation | Quotation Register
Execution Commencement | Start approved execution work | Interior Designer | Stage-based vendor payment eligible | Execution Checklist | Execution Tracker
Progress Reporting | Provide work progress updates | Interior Designer | Invoice subject to milestone approval | Progress Reports | Project Monitoring
Invoice Submission | Submit invoice to Seventh Sky | Interior Designer | No direct client invoicing permitted | Vendor Invoice | Finance Register
Payment Verification | Verify completed milestone | Finance & Operations | Approve vendor payment | Inspection Record | Payment Approval Log
Vendor Payment | Disburse approved vendor payment | Finance Team | Transfer payment to vendor account | Payment Record | Finance Register
Final Completion | Complete project closure | Interior Designer | Final settlement after client sign-off | Completion Record | Closure Register

## Vendor Enterprise WF
Department | Enterprise Workflow Process | Key Actions | Payment Control | Required Evidence | Reporting Requirement | Escalation Trigger
Vendor Management | Vendor Registration | Approve subcontractor onboarding | Verify vendor bank/payment details | Vendor Agreement | Vendor Register | Unverified vendor
Project Coordination | Project Allocation | Assign project and issue work order | Internal costing review | Project Allocation Form | Allocation Report | Pricing conflict
Interior Design Coordination | Design Planning | Coordinate concept development | No direct payment to vendor from client | Design Notes | Design Workflow | Direct client communication
Finance | Quotation Review | Review vendor quotation | Margin & pricing review | Vendor Quotation | Finance Update | Pricing discrepancy
Operations | Execution Monitoring | Monitor execution workflow | Milestone verification | Execution Reports | Execution Report | Poor workmanship
Finance | Invoice Verification | Verify milestone invoice | Cross-check against project progress | Vendor Invoice | Finance Register | Unapproved invoice
Finance | Vendor Payment Disbursement | Release approved vendor payment | Payment authorisation required | Payment Record | Payment Report | Payment dispute
Compliance | Non-Circumvention Monitoring | Monitor bypass or private dealing | Commission protection review | Communication Records | Compliance Report | Direct client bypass
Operations | Project Completion | Final inspection and completion sign-off | Final payment reconciliation | Completion Checklist | Closure Report | Outstanding defect