## End User Workflow
Workflow Stage | Task / Activity | Responsible Team | Client Payment Workflow | Vendor Payment Workflow | Required Documents | CRM / System Update | Status | Remarks
Lead Intake | Receive client enquiry and register project | Client Relations | No payment at this stage | No vendor payment | Client Intake Form | Lead Register
Consultation | Conduct consultation and requirement analysis | Space Planning Team | Collect consultation fee | No vendor payment | Consultation Notes | Consultation Tracker
Site Assessment | Conduct site inspection and measurements | Operations Team | Collect assessment fee | Assessment fee payable after approval | Inspection Report | Inspection Register
Quotation & Proposal | Prepare quotation and project scope | Finance & Coordination | Issue quotation and stage payment schedule | Internal vendor costing review | Quotation | Quotation Register
Agreement Execution | Execute agreement and onboarding | Documentation Team | Collect initial project deposit | Vendor onboarding verification | Signed Agreement | Agreement Register
Design & Planning | Prepare layout and renovation concepts | Interior Design Coordination | Collect Stage 2 planning payment | Release planning milestone payment | Design Concepts | Planning Tracker
Execution Coordination | Coordinate renovation and fit-out work | Project Coordinator | Collect execution stage payment | Release approved vendor milestone payment | Execution Checklist | Execution Register
Variation Management | Manage project changes and variations | Project Coordinator | Collect approved variation charges | Approve revised vendor payment | Variation Form | Variation Register
Quality Inspection | Conduct quality and completion review | Quality Control Team | Collect outstanding balance | Hold retention until sign-off | QC Checklist | QC Register
Final Vendor Settlement | Release final vendor payment | Finance Team | Confirm client payment clearance | Final vendor settlement | Settlement Record | Finance Register
Project Handover | Complete handover and project closure | Operations Team | Confirm all dues cleared | Close vendor payment file | Handover Report | Closure Register

## End User Enterprise WF
Department | Enterprise Workflow Process | Key Actions | Client Payment Control | Vendor Payment Control | Required Evidence | Reporting Requirement | Escalation Trigger
Client Relations | Lead Intake & Consultation | Register client and collect requirements | Consultation fee verification | No vendor payment | Client Intake Form | CRM Update | Fake client details
Operations | Property Assessment | Conduct inspection and planning assessment | Assessment fee confirmation | Assessment fee review | Inspection Report | Assessment Report | Unsafe property condition
Finance | Quotation & Deposit | Issue quotation and collect deposit | Deposit verification | Vendor budget review | Quotation & Receipt | Finance Update | Payment default
Planning Team | Space Planning & Design | Coordinate planning and design workflow | Planning payment verification | Planning milestone release | Concept Plans | Planning Report | Scope conflict
Project Coordination | Execution Coordination | Coordinate renovation workflow | Execution payment tracking | Vendor milestone verification | Execution Reports | Execution Update | Project delay
Finance | Variation & Cost Approval | Approve variations and revised pricing | Variation charge collection | Variation payment approval | Variation Form | Variation Report | Unauthorised variation
Quality Control | Final Inspection | Conduct project quality review | Final balance clearance | Vendor retention verification | QC Checklist | QC Report | Major defect
Finance | Vendor Final Settlement | Release final vendor payment | Client payment reconciliation | Final settlement approval | Settlement Record | Settlement Report | Outstanding dues
Operations | Project Closure | Complete handover and closure | Confirm all client payments cleared | Close vendor account | Handover Report | Closure Report | Client dispute

## Vendor Workflow
Workflow Stage | Task / Activity | Responsible Party | Client Payment Workflow | Vendor Payment Workflow | Required Documents | CRM / System Update | Status | Remarks
Vendor Registration | Register approved vendor/service provider | Vendor Management Team | No client payment access | No payment at onboarding | Vendor Agreement | Vendor Register
Project Allocation | Assign project and issue work order | Project Coordinator | Client handled by Seventh Sky only | Approved vendor costing | Project Allocation Form | Vendor Tracker
Planning & Design | Prepare layout and planning concepts | Vendor/Interior Planner | No direct client payment allowed | Planning milestone eligible | Planning Notes | Planning Workflow
Quotation Submission | Submit internal quotation | Vendor | No direct client quotation permitted | Quotation review pending | Vendor Quotation | Quotation Register
Execution Commencement | Start approved renovation work | Vendor | Client payment controlled by Seventh Sky | Execution payment eligibility | Execution Checklist | Execution Register
Progress Reporting | Provide progress updates and site reports | Vendor | No direct payment collection | Invoice subject to milestone approval | Progress Reports | Monitoring Register
Invoice Submission | Submit invoice to Seventh Sky | Vendor | No client invoicing permitted | Vendor invoice review | Vendor Invoice | Finance Register
Payment Verification | Verify milestone completion | Finance & Operations | Client payment verification | Approve vendor payment | Inspection Report | Approval Register
Vendor Payment | Disburse approved payment | Finance Team | Client settlement confirmation | Vendor payment release | Payment Record | Finance Register
Final Completion | Complete project closure | Vendor | Client sign-off verification | Final vendor settlement | Completion Record | Closure Register

## Vendor Enterprise WF
Department | Enterprise Workflow Process | Key Actions | Client Payment Control | Vendor Payment Control | Required Evidence | Reporting Requirement | Escalation Trigger
Vendor Management | Vendor Registration & Approval | Approve vendor onboarding | No direct client payment authority | Verify bank/payment details | Vendor Agreement | Vendor Register | Unverified vendor
Project Coordination | Project Allocation | Assign project and issue work order | Client handled through Seventh Sky | Internal costing review | Project Allocation Form | Allocation Report | Pricing conflict
Planning Team | Planning & Concept Development | Coordinate space planning workflow | No direct client dealing | Planning milestone verification | Concept Notes | Planning Report | Direct client communication
Finance | Quotation Review | Review vendor pricing | Client pricing confidential | Vendor pricing approval | Vendor Quotation | Finance Update | Pricing inconsistency
Operations | Execution Monitoring | Monitor execution and renovation work | No vendor collection from client | Milestone verification | Execution Reports | Execution Report | Poor workmanship
Finance | Invoice Verification | Verify vendor invoices | Client payment reconciliation | Vendor invoice approval | Vendor Invoice | Finance Register | Unapproved invoice
Finance | Vendor Payment Disbursement | Release approved payment | Client dues confirmation | Payment authorisation required | Payment Record | Payment Report | Payment dispute
Compliance | Non-Circumvention Monitoring | Monitor bypass or direct dealing | Commission protection review | Vendor conduct monitoring | Communication Records | Compliance Report | Direct client bypass
Operations | Project Completion | Final inspection and project closure | Final client clearance | Vendor final settlement | Completion Checklist | Closure Report | Outstanding defect