SEVENTH SKY PROPERTY CARE

PROPERTY CARE AND CONCIERGE SERVICES

STANDARD OPERATING PROCEDURE (SOP)

CLIENT / END USER MANAGEMENT

Document No: SSPC-PCCS-SOP-01
Version: 0.1
Effective Date: __________
Division: Seventh Sky Property Care and Concierge Services

Table of Contents

1. PURPOSE	3

2. SCOPE	3

3. RESPONSIBILITIES	4

4. PHASE 1 – CLIENT ACQUISITION	5

5. PHASE 2 – CONSULTATION & NEEDS ANALYSIS	5

6. PHASE 3 – COMMERCIAL APPROVAL	6

7. PHASE 4 – SERVICE ALLOCATION	6

8. PHASE 5 – SERVICE DELIVERY	6

9. PHASE 6 – QUALITY CONTROL	7

10. PHASE 7 – COMPLETION	7

11. INSURANCE PROCEDURE	7

12. RECORD RETENTION	8

# 1. PURPOSE

To establish a standardised process for managing, coordinating and delivering auxiliary property services to clients through Seventh Sky Property Care.

# 2. SCOPE

Applies to all MAPS services including:

Property Care Services

- Cleaning

- Gardening

- Caretaker Coordination

- Utility Coordination

Repairs & Maintenance

- General Repairs

- Painting

- Renovation Coordination

Inspection Services

- Entry Inspection

- Routine Inspection

- Exit Inspection

Smart Property Services

- CCTV Installation

- Smart Lock Installation

- Smart Home Setup

Security Services

- Property Monitoring

- Vacant Property Checks

- Security Guard Coordination

Marketing Services

- Photography

- Videography

- Drone Services

NRB Services

- Property Monitoring

- Video Inspections

- Overseas Reporting

# 3. RESPONSIBILITIES

Business Development Officer

Responsible for:

- Lead generation

- Enquiry management

- Initial consultation

Property Services Coordinator

Responsible for:

- Project coordination

- Service scheduling

- Client communication

- Service provider allocation

Operations Manager

Responsible for:

- Escalation management

- Service quality monitoring

- Vendor management

Finance Officer

Responsible for:

- Invoicing

- Payment collection

- Contractor payment approval

# 4. PHASE 1 – CLIENT ACQUISITION

Step 1

Receive enquiry.

Sources:

- Website

- Referral

- Facebook

- Walk-in

- Existing Client

Step 2

Create Client Record.

Step 3

Create Project Reference Number.

Example:

MAPS-2026-001

# 5. PHASE 2 – CONSULTATION & NEEDS ANALYSIS

Step 4

Determine:

- Service required

- Property type

- Budget

- Urgency

- Access requirements

- Special instructions

Step 5

Conduct site inspection if required.

# 6. PHASE 3 – COMMERCIAL APPROVAL

Step 6

Issue quotation.

Step 7

Issue MAPSA Agreement.

Step 8

Obtain:

- Signed Agreement

- Deposit (if applicable)

No work commences until approval is received.

# 7. PHASE 4 – SERVICE ALLOCATION

Step 9

Identify suitable service provider.

Step 10

Verify:

- PSPA active

- Insurance valid

- Capacity available

Step 11

Issue Service Work Order.

# 8. PHASE 5 – SERVICE DELIVERY

Step 12

Coordinate commencement.

Step 13

Monitor:

- Timeline

- Quality

- Client satisfaction

Step 14

Collect:

- Photos

- Reports

- Evidence

where applicable.

# 9. PHASE 6 – QUALITY CONTROL

Step 15

Review service outcome.

Step 16

Record defects or complaints.

Step 17

Coordinate rectification.

# 10. PHASE 7 – COMPLETION

Step 18

Confirm completion.

Step 19

Issue final invoice.

Step 20

Collect payment.

Step 21

Obtain client feedback.

Step 22

Close project file.

# 11. INSURANCE PROCEDURE

Where applicable:

- Offer insurance coordination

- Record client decision

- Retain documentation

# 12. RECORD RETENTION

Maintain:

- Agreements

- Quotes

- Work Orders

- Photos

- Reports

- Invoices

Minimum:

Seven (7) Years