## Dashboard
SEVENTH SKY PROPERTY CARE - RESIDENTIAL PROPERTY PURCHASE SERVICE WORKFLOW & CHECKLIST V2.0
Purpose | Detailed Excel workflow and checklist template for managing clients who purchase residential property through Seventh Sky.
Based On | Residential Property Purchase Service Agreement V0.1, including buyer requirements, scope of services, buyer responsibilities, document disclaimer, phases, fee structure, non-circumvention, communication records and exit clauses.
Client Journey | Enquiry → Buyer Requirement → Phase 1 Consultation → Agreement/Payment → Phase 2 Search → Inspection → Document Verification → Negotiation → Agreement Coordination → Settlement/Registration → Handover → Closure.
Core Control | No transaction should proceed without buyer approval, document verification coordination, written communication records and fee/commission protection controls.
CRM Automation | Auto IDs, buyer profile, property shortlist, inspection scheduling, document checklist, approval records, negotiation log, fee tracker, settlement reminders and KPI dashboard.
Risk Controls | Seller document risks, hidden disputes, financing failure, buyer circumvention, unpaid fees, seller withdrawal, registration delays and third-party professional advice tracking.
Recommended Use | Use as internal operational workflow, Renetech CRM development blueprint and staff task checklist.
Workbook Version | V2.0 - detailed populated version
Prepared For | Seventh Sky Residential Property Services
Brand Principle | Built on Trust, Driven by Care
Dashboard Inputs | Use KPI Dashboard Data, Project Register, Fee Register and Risk Register to prepare live dashboard once CRM is operational.
Agreement Requirement | Buyer Service Agreement must be signed before active buyer support and introduced property negotiations.
Evidence Requirement | CRM records, email, WhatsApp, call logs, inspection records, visitor logs and approvals should be stored as evidence.
Status | Ready for operational use and CRM conversion.

## Lists & Status Values
List Type | Value | Use In Sheet | Notes
Lead Status | New Lead | Buyer Master Register | New buyer enquiry received
Lead Status | Contacted | Buyer Master Register | Buyer contacted by Seventh Sky
Lead Status | Consultation Scheduled | Consultation Register | Initial buyer consultation booked
Lead Status | Phase 1 Completed | Consultation Register | Buyer requirement and feasibility reviewed
Lead Status | Agreement Sent | Agreement Register | Purchase service agreement sent
Lead Status | Agreement Signed | Agreement Register | Agreement executed
Lead Status | Phase 2 Active | Project Register | Active property search and buyer support
Lead Status | Property Shortlisted | Property Shortlist | One or more properties shortlisted
Lead Status | Inspection Scheduled | Inspection Register | Inspection booked
Lead Status | Offer Stage | Negotiation Tracker | Buyer considering/submitting offer
Lead Status | Settlement Stage | Settlement Register | Agreement/registration support underway
Lead Status | Completed | Project Closure | Purchase process completed
Lead Status | Closed - No Purchase | Project Closure | Client withdrew or no suitable property
Priority | Low | Tasks/Risks | Routine
Priority | Medium | Tasks/Risks | Moderate attention
Priority | High | Tasks/Risks | Urgent business/legal risk
Priority | Critical | Tasks/Risks | Immediate attention required
Property Type | Apartment | Buyer Requirements | Preferred property category
Property Type | House | Buyer Requirements | Preferred property category
Property Type | Duplex | Buyer Requirements | Preferred property category
Property Type | Land | Buyer Requirements | Preferred property category
Property Type | Furnished Property | Buyer Requirements | Preferred property category
Purchase Purpose | Personal Residence | Buyer Requirements | Buyer intent
Purchase Purpose | Investment | Buyer Requirements | Buyer intent
Purchase Purpose | NRB Investment | Buyer Requirements | Buyer intent
Purchase Purpose | Family Purpose | Buyer Requirements | Buyer intent
Finance Source | Cash Purchase | Buyer Requirements | Funding type
Finance Source | Bank Loan | Buyer Requirements | Funding type
Finance Source | Partial Loan | Buyer Requirements | Funding type
Finance Source | Other | Buyer Requirements | Funding type
Document Status | Not Received | Document Verification | Document not yet provided
Document Status | Received | Document Verification | Document collected
Document Status | Under Review | Document Verification | Review being coordinated
Document Status | Verified / No Concern Noted | Document Verification | No immediate concern noted
Document Status | Concern Identified | Document Verification | Issue needs escalation
Document Status | External Advice Required | Document Verification | Lawyer/valuer/surveyor required
Decision | Proceed | Stage Gate Register | Move to next stage
Decision | Hold | Stage Gate Register | Pause pending clarification
Decision | Reject / Stop | Stage Gate Register | Do not proceed

## Buyer Master Register
Buyer ID | Project ID | Buyer Name | Client Type | Mobile | Email | NID/Passport | Current Address | Preferred Locations | Preferred Property Type | Budget Range | Finance Source | Purchase Purpose | Current Status | Assigned Officer | Next Action | Next Follow-Up | Notes
BUY-C0001 | BUY-P0001 | Sample Buyer - Personal Residence | Residential Buyer | 01XXXXXXXXX | buyer1@example.com | Pending | Cumilla | Cumilla Sadar, Kandirpar | Apartment | BDT 80L - 1.2Cr | Cash Purchase | Personal Residence | New Lead | Buyer Support Coordinator | Schedule consultation |  | Example only
BUY-C0002 | BUY-P0002 | Sample NRB Buyer | NRB Buyer | 01XXXXXXXXX | nrb@example.com | Passport pending | Overseas | Cumilla / Dhaka | House | BDT 1.5Cr - 2.5Cr | Bank Loan / Cash | NRB Investment | Consultation Scheduled | Buyer Support Coordinator | Collect requirements and finance details |  | Example only
BUY-C0003 | BUY-P0003 | Sample Investor | Investor | 01XXXXXXXXX | investor@example.com | Pending | Dhaka | Cumilla emerging areas | Land | BDT 50L - 1Cr | Cash Purchase | Investment | Phase 1 Completed | Residential Services Manager | Send agreement for Phase 2 |  | Example only
BUY-C0004 | BUY-P0004 | Sample Family Buyer | Residential Buyer | 01XXXXXXXXX | family@example.com | Pending | Cumilla | Near school and transport | House | BDT 1Cr - 1.8Cr | Partial Loan | Family Purpose | Property Shortlisted | Buyer Support Coordinator | Arrange inspections |  | Example only
BUY-C0005 | BUY-P0005 | Sample Furnished Property Buyer | Residential Buyer | 01XXXXXXXXX | furnished@example.com | Pending | Comilla | Central Comilla | Furnished Apartment | BDT 90L - 1.4Cr | Cash Purchase | Personal Residence | Offer Stage | Buyer Support Coordinator | Prepare offer approval |  | Example only

## Buyer Requirement Form
Requirement ID | Buyer ID | Project ID | Requirement Area | Requirement Details | Priority | Mandatory? | Buyer Confirmation | Notes
REQ-0001 | BUY-C0001 | BUY-P0001 | Property Type | Apartment, minimum 3 bedrooms | High | Yes | Pending
REQ-0002 | BUY-C0001 | BUY-P0001 | Location | Cumilla Sadar or Kandirpar | High | Yes | Pending
REQ-0003 | BUY-C0001 | BUY-P0001 | Budget | BDT 80L - 1.2Cr including key costs | High | Yes | Pending
REQ-0004 | BUY-C0001 | BUY-P0001 | Finance Source | Cash purchase; proof of funds to be confirmed | High | Yes | Pending
REQ-0005 | BUY-C0002 | BUY-P0002 | NRB Support | Remote inspection, video reporting, document coordination | High | Yes | Pending
REQ-0006 | BUY-C0003 | BUY-P0003 | Investment Criteria | Growth location, resale potential, clean title | High | Yes | Pending
REQ-0007 | BUY-C0004 | BUY-P0004 | Family Needs | School access, safety, utilities, low maintenance | High | Yes | Pending
REQ-0008 | BUY-C0005 | BUY-P0005 | Furnished Requirement | Furnished property with handover inventory | Medium | No | Pending
REQ-0009 | BUY-C0005 | BUY-P0005 | Move-in Readiness | Utility setup, cleaning, repair review | Medium | No | Pending | Upsell property care service

## Consultation & Phase 1
Consultation ID | Buyer ID | Project ID | Consultation Date | Topics Covered | Budget Discussed | Finance Readiness | Market Feasibility | Concerns Identified | Recommendation | Phase 1 Fee | Payment Status | Proceed to Phase 2? | Officer Notes
CON-0001 | BUY-C0001 | BUY-P0001 |  | Buyer goals, budget, preferred location, finance readiness | Yes | To be verified | Likely feasible | Proof of funds pending | Proceed after KYC and finance confirmation | BDT ______ | Pending | Hold
CON-0002 | BUY-C0002 | BUY-P0002 |  | NRB investment goals, remote coordination, caretaker contact | Yes | Loan/cash mix uncertain | Possible | Remote document review required | Proceed after agreement and local contact verification | BDT ______ | Pending | Hold | NRB
CON-0003 | BUY-C0003 | BUY-P0003 |  | Investment strategy, land risk, verification needs | Yes | Cash buyer | Feasible | Title risk for land purchases | Proceed to Phase 2 with strict document checks | BDT ______ | Paid | Yes
CON-0004 | BUY-C0004 | BUY-P0004 |  | Family residence needs and inspection criteria | Yes | Partial loan | Feasible if bank pre-approval obtained | Bank approval pending | Proceed with inspection after finance confirmation | BDT ______ | Paid | Yes

## Agreement & Engagement Register
Agreement ID | Buyer ID | Project ID | Agreement Type | Phase | Sent Date | Signed Date | Exclusive Period Start | Exclusive Period End | Service Fee Type | Service Fee/Commission | Agreement Status | Storage Link | Remarks
AGR-0001 | BUY-C0001 | BUY-P0001 | Residential Property Purchase Service Agreement | Phase 1 |  |  |  |  | Fixed/Stage Fee | BDT ______ | Draft |  | Initial engagement
AGR-0002 | BUY-C0002 | BUY-P0002 | Residential Property Purchase Service Agreement | Phase 1/2 |  |  |  |  | Stage + Success Fee | BDT ______ / ____% | Pending Signature |  | NRB buyer
AGR-0003 | BUY-C0003 | BUY-P0003 | Residential Property Purchase Service Agreement | Phase 2 |  |  |  |  | Percentage-Based Commission | ____% of purchase value | Signed |  | 90-day exclusivity
AGR-0004 | BUY-C0004 | BUY-P0004 | Residential Property Purchase Service Agreement | Phase 2 |  |  |  |  | Combination | Fixed + success fee | Signed

## Property Sourcing Tracker
Source ID | Project ID | Buyer ID | Search Date | Property Source | Seller/Agent/Owner | Contact Details | Property Type | Location | Asking Price | Availability Confirmed | Matches Buyer Criteria? | Risk Notes | Next Action | Status
SRC-0001 | BUY-P0001 | BUY-C0001 |  | Owner Network | Owner TBC | TBC | Apartment | Cumilla Sadar | BDT 1.05Cr | Pending | Likely | Ownership docs not yet reviewed | Request property documents | Open
SRC-0002 | BUY-P0002 | BUY-C0002 |  | Developer Network | Developer TBC | TBC | House | Cumilla | BDT 2.1Cr | Pending | Yes | Need construction approval and title check | Arrange remote video walkthrough | Open
SRC-0003 | BUY-P0003 | BUY-C0003 |  | Local Agent | Agent TBC | TBC | Land | Emerging Cumilla area | BDT 75L | Yes | Yes | Land title/survey risk | Collect deed, mutation and survey | Open
SRC-0004 | BUY-P0004 | BUY-C0004 |  | Seller Referral | Seller TBC | TBC | House | Near school | BDT 1.45Cr | Yes | Yes | Bank valuation needed | Schedule inspection | Shortlisted
SRC-0005 | BUY-P0005 | BUY-C0005 |  | Online Listing | Agent TBC | TBC | Furnished Apartment | Central Comilla | BDT 1.25Cr | Yes | Yes | Inventory verification needed | Arrange viewing | Shortlisted

## Property Shortlist & Compare
Shortlist ID | Project ID | Buyer ID | Property Ref | Location | Property Type | Asking Price | Estimated Market Fit | Budget Fit | Legal Risk | Physical Condition | Finance Suitability | Score / 100 | Buyer Decision | Notes
SL-0001 | BUY-P0001 | BUY-C0001 | PROP-001 | Cumilla Sadar | Apartment | BDT 1.05Cr | Good | Yes | Unknown | Unknown | Likely | 70 | Pending | Need inspection and documents
SL-0002 | BUY-P0002 | BUY-C0002 | PROP-002 | Cumilla | House | BDT 2.1Cr | Good | Yes | Medium | Unknown | Loan-dependent | 68 | Pending | NRB remote report required
SL-0003 | BUY-P0003 | BUY-C0003 | PROP-003 | Emerging area | Land | BDT 75L | Good | Yes | High | N/A | Cash | 62 | Hold | Land documents need strict review
SL-0004 | BUY-P0004 | BUY-C0004 | PROP-004 | Near school | House | BDT 1.45Cr | Very good | Yes | Unknown | Good based on photos | Bank dependent | 82 | Inspect | Good family fit
SL-0005 | BUY-P0005 | BUY-C0005 | PROP-005 | Central Comilla | Furnished Apartment | BDT 1.25Cr | Good | Yes | Unknown | Good based on listing | Cash | 78 | Inspect | Need furniture inventory

## Inspection Schedule
Inspection ID | Project ID | Buyer ID | Property Ref | Inspection Date | Inspection Mode | Buyer Attending? | Seventh Sky Attending? | Seller/Agent Contact | Access Details | Photos Required | Video Required | Inspection Status | Follow-Up Action
INSP-0001 | BUY-P0001 | BUY-C0001 | PROP-001 |  | Physical | Yes | Yes | TBC | Owner access | Yes | Optional | Planned | Confirm seller access
INSP-0002 | BUY-P0002 | BUY-C0002 | PROP-002 |  | Remote Video | No - NRB | Yes | TBC | Caretaker/seller access | Yes | Yes | Planned | Schedule video call
INSP-0003 | BUY-P0004 | BUY-C0004 | PROP-004 |  | Physical | Yes | Yes | TBC | Agent access | Yes | Optional | Scheduled | Prepare checklist
INSP-0004 | BUY-P0005 | BUY-C0005 | PROP-005 |  | Physical | Yes | Yes | Agent TBC | Agent access | Yes | Yes | Planned | Verify furniture list

## Inspection Checklist
Checklist ID | Inspection ID | Category | Inspection Item | Required? | Finding / Result | Risk Rating | Evidence Required | Action Required | Responsible
IC-001 | INSP-0001 | General | Confirm property address and identity | Yes |  | Medium | Photos / location record | Verify with documents | Inspection Officer
IC-002 | INSP-0001 | Access | Road access and entrance condition | Yes |  | Medium | Photos | Note access concerns | Inspection Officer
IC-003 | INSP-0001 | Structure | External wall/structural visible condition | Yes |  | High | Photos/video | Escalate if cracks visible | Inspection Officer
IC-004 | INSP-0001 | Structure | Ceiling, floor and water leakage signs | Yes |  | High | Photos | Recommend engineer if concern | Inspection Officer
IC-005 | INSP-0001 | Utilities | Electricity connection and meter availability | Yes |  | Medium | Photo of meter if possible | Verify utility status | Inspection Officer
IC-006 | INSP-0001 | Utilities | Water, gas and drainage availability | Yes |  | Medium | Photos/notes | Record missing utilities | Inspection Officer
IC-007 | INSP-0001 | Safety | Neighbourhood and security condition | Yes |  | Medium | Notes/photos | Report safety concerns | Inspection Officer
IC-008 | INSP-0001 | Legal Indicator | Occupancy status and possession clarity | Yes |  | High | Photos, seller statement | Check possession risk | Coordinator
IC-009 | INSP-0001 | Condition | Doors, windows, kitchen, bathrooms condition | Yes |  | Medium | Photos | Estimate repair costs if required | Inspection Officer
IC-010 | INSP-0001 | Location | School, transport, market, mosque, road proximity | If relevant |  | Low | Notes/photos | Compare with buyer needs | Coordinator
IC-011 | INSP-0001 | Apartment Specific | Lift, common area, parking, association fees | If apartment |  | Medium | Photos/records | Verify ongoing fees | Coordinator
IC-012 | INSP-0001 | Land Specific | Boundary, access road, occupation, encroachment signs | If land |  | High | Photos/video/survey support | Recommend surveyor | Coordinator
IC-013 | INSP-0001 | Furnished Property | Furniture inventory and condition | If furnished |  | Medium | Photo inventory | Prepare handover inventory | Coordinator
IC-014 | INSP-0001 | Commercial Value | Estimated repair / readiness cost | Yes |  | Medium | Notes/quote | Share with buyer | Coordinator
IC-015 | INSP-0001 | Buyer Decision | Buyer proceed / hold / reject decision recorded | Yes |  | High | Written approval | Update property status | Buyer Support Coordinator

## Document Verification Register
Document ID | Project ID | Buyer ID | Property Ref | Document Type | Received From | Received Date | Review Status | Concern Identified | External Professional Required | Action Required | Responsible | Due Date | Notes
DOC-001 | BUY-P0001 | BUY-C0001 | PROP-001 | Title Deed | Seller/Agent |  | Not Received |  | Lawyer recommended | Request copy | Coordinator
DOC-002 | BUY-P0001 | BUY-C0001 | PROP-001 | Mutation Document | Seller/Agent |  | Not Received |  | Lawyer recommended | Request copy | Coordinator
DOC-003 | BUY-P0001 | BUY-C0001 | PROP-001 | Khatian / Record of Rights | Seller/Agent |  | Not Received |  | Lawyer recommended | Request copy | Coordinator
DOC-004 | BUY-P0001 | BUY-C0001 | PROP-001 | Tax / Holding / Rent Receipt | Seller/Agent |  | Not Received |  | Tax/legal review | Request latest record | Coordinator
DOC-005 | BUY-P0001 | BUY-C0001 | PROP-001 | Utility Bills | Seller/Agent |  | Not Received |  | Optional | Request copies | Coordinator
DOC-006 | BUY-P0001 | BUY-C0001 | PROP-001 | Survey / Site Plan | Seller/Agent |  | Not Received |  | Surveyor if land/house | Request copy | Coordinator
DOC-007 | BUY-P0001 | BUY-C0001 | PROP-001 | Succession / Heirship Documents | Seller/Agent |  | If applicable |  | Lawyer required | Ask applicability | Coordinator
DOC-008 | BUY-P0001 | BUY-C0001 | PROP-001 | Court Case / Encumbrance Disclosure | Seller/Agent |  | Pending |  | Lawyer recommended | Obtain seller declaration | Coordinator
DOC-009 | BUY-P0005 | BUY-C0005 | PROP-005 | Furniture Inventory | Seller/Agent |  | Not Received |  | No | Request inventory list | Coordinator |  | Furnished property

## Professional Advice Tracker
Advice ID | Project ID | Buyer ID | Property Ref | Professional Type | Professional Name | Purpose | Engaged By | Cost Responsibility | Status | Advice Received Date | Key Finding | Next Action
ADV-001 | BUY-P0001 | BUY-C0001 | PROP-001 | Lawyer | TBC | Ownership and deed review | Buyer / Seventh Sky coordination | Buyer | Not Started |  |  | Obtain documents first
ADV-002 | BUY-P0003 | BUY-C0003 | PROP-003 | Surveyor | TBC | Boundary and land measurement | Buyer / Seventh Sky coordination | Buyer | Not Started |  |  | Arrange after shortlist approval
ADV-003 | BUY-P0004 | BUY-C0004 | PROP-004 | Bank / Finance Adviser | TBC | Loan readiness and valuation | Buyer | Buyer | Pending |  |  | Buyer to provide update
ADV-004 | BUY-P0005 | BUY-C0005 | PROP-005 | Valuer | TBC | Market value check | Buyer / Seventh Sky coordination | Buyer | Optional |  |  | Buyer decision required
ADV-005 | BUY-P0002 | BUY-C0002 | PROP-002 | Engineer | TBC | Structural review for house | Buyer / Seventh Sky coordination | Buyer | Optional |  |  | Needed if visible structural concern

## Risk Assessment Register
Risk ID | Project ID | Buyer ID | Property Ref | Risk Category | Risk Description | Likelihood | Impact | Risk Rating | Mitigation / Control | Owner | Status
RISK-001 | BUY-P0001 | BUY-C0001 | PROP-001 | Document Risk | Seller documents may be incomplete or unverifiable | Medium | High | High | Coordinate lawyer review and obtain written buyer acknowledgement | Coordinator | Open
RISK-002 | BUY-P0002 | BUY-C0002 | PROP-002 | NRB Remote Risk | Buyer cannot physically inspect property | Medium | High | High | Use video inspection, photos, local representative and written approval | Coordinator | Open
RISK-003 | BUY-P0003 | BUY-C0003 | PROP-003 | Land Boundary Risk | Land boundary/possession may be unclear | High | High | Critical | Require surveyor and legal review before offer | Coordinator | Open
RISK-004 | BUY-P0004 | BUY-C0004 | PROP-004 | Finance Risk | Bank loan may not be approved | Medium | High | High | Buyer must independently verify financing capability | Buyer | Open
RISK-005 | BUY-P0005 | BUY-C0005 | PROP-005 | Handover Risk | Furniture or inclusions may not match expectation | Medium | Medium | Medium | Prepare written inventory and photo evidence | Coordinator | Open
RISK-006 | ALL | ALL | ALL | Circumvention Risk | Buyer may directly negotiate with introduced seller | Medium | High | High | Enforce non-circumvention and protected introduction register | Manager | Open
RISK-007 | ALL | ALL | ALL | Market Risk | Property value or market condition may change | Medium | Medium | Medium | Clarify no guarantee of market value or investment outcome | Manager | Open

## Protected Introduction Register
Protected ID | Project ID | Buyer ID | Property Ref | Seller / Owner / Agent | Introduction Date | Protected Until | Introduced By | Communication Channel | Direct Communication Allowed? | Breach Risk | Notes
PI-0001 | BUY-P0001 | BUY-C0001 | PROP-001 | Owner TBC |  | 12 months after introduction | Seventh Sky | Phone/CRM/WhatsApp | No unless approved | Medium
PI-0002 | BUY-P0002 | BUY-C0002 | PROP-002 | Developer TBC |  | 12 months after introduction | Seventh Sky | CRM/Email | No unless approved | Medium | NRB buyer
PI-0003 | BUY-P0003 | BUY-C0003 | PROP-003 | Agent TBC |  | 12 months after introduction | Seventh Sky | Phone/WhatsApp | No unless approved | High | Land purchase
PI-0004 | BUY-P0004 | BUY-C0004 | PROP-004 | Seller TBC |  | 12 months after introduction | Seventh Sky | Inspection booking | No unless approved | Medium
PI-0005 | BUY-P0005 | BUY-C0005 | PROP-005 | Agent TBC |  | 12 months after introduction | Seventh Sky | Listing/inspection | No unless approved | Medium

## Negotiation Tracker
Negotiation ID | Project ID | Buyer ID | Property Ref | Date | Offer / Discussion Type | Buyer Approved Offer | Seller Asking / Counter | Current Position | Decision Required | Approval Evidence | Status | Notes
NEG-0001 | BUY-P0005 | BUY-C0005 | PROP-005 |  | Initial Offer | BDT ______ | BDT 1.25Cr | Buyer considering lower offer | Buyer written approval | Pending | Draft
NEG-0002 | BUY-P0004 | BUY-C0004 | PROP-004 |  | Inspection Feedback | Not yet |  | Await inspection | Buyer decision after inspection | Pending | Planned
NEG-0003 | BUY-P0003 | BUY-C0003 | PROP-003 |  | Price Discussion | TBC | BDT 75L | Hold pending document review | Legal/survey result first | Pending | Hold

## Offer Approval Checklist
Approval ID | Project ID | Buyer ID | Property Ref | Checklist Item | Required? | Status | Evidence | Responsible | Notes
OA-001 | BUY-P0005 | BUY-C0005 | PROP-005 | Buyer has inspected or accepted remote inspection | Yes | Pending | Inspection report/video | Coordinator
OA-002 | BUY-P0005 | BUY-C0005 | PROP-005 | Buyer has approved offer amount in writing | Yes | Pending | Email/WhatsApp/CRM approval | Buyer
OA-003 | BUY-P0005 | BUY-C0005 | PROP-005 | Document verification concerns disclosed | Yes | Pending | Verification summary | Coordinator
OA-004 | BUY-P0005 | BUY-C0005 | PROP-005 | External legal advice recommended / acknowledged | Yes | Pending | Lawyer record or buyer waiver | Buyer
OA-005 | BUY-P0005 | BUY-C0005 | PROP-005 | Financing readiness confirmed | Yes | Pending | Buyer declaration / bank note | Buyer
OA-006 | BUY-P0005 | BUY-C0005 | PROP-005 | Deposit/payment readiness confirmed | Yes | Pending | Buyer confirmation | Buyer
OA-007 | BUY-P0005 | BUY-C0005 | PROP-005 | Seventh Sky fee/commission acknowledged | Yes | Pending | Agreement / invoice | Coordinator
OA-008 | BUY-P0005 | BUY-C0005 | PROP-005 | Non-circumvention obligations reminded | Yes | Pending | CRM note | Coordinator

## Transaction Coordination
Transaction ID | Project ID | Buyer ID | Property Ref | Seller | Agreed Price | Agreement Drafted? | Deposit Paid? | Legal Review Done? | Registration Prep Status | Settlement Target | Current Stage | Next Action | Notes
TRX-0001 | BUY-P0005 | BUY-C0005 | PROP-005 | Seller/Agent TBC | TBC | No | No | No | Not Started |  | Offer stage | Await buyer offer approval
TRX-0002 | BUY-P0004 | BUY-C0004 | PROP-004 | Seller TBC | TBC | No | No | No | Not Started |  | Pre-offer | Complete inspection first

## Settlement & Registration
Settlement ID | Project ID | Buyer ID | Property Ref | Lawyer/Deed Writer | Stamp Duty Checked | Registration Fee Checked | Funds Ready | Settlement Date | Registration Date | Possession Date | Handover Status | Outstanding Issues | Status
SET-0001 | BUY-P0005 | BUY-C0005 | PROP-005 | TBC | No | No | No |  |  |  | Not Started | Await transaction agreement | Planned
SET-0002 | BUY-P0004 | BUY-C0004 | PROP-004 | TBC | No | No | No |  |  |  | Not Started | Pre-offer stage | Future

## Fees & Commission Register
Fee ID | Project ID | Buyer ID | Fee Type | Basis | Amount / Percentage | Invoice Date | Due Date | Paid Amount | Outstanding | Payment Status | Trigger Event | Notes
FEE-0001 | BUY-P0001 | BUY-C0001 | Phase 1 Fee | Fixed | BDT ______ |  |  | BDT 0 | BDT ______ | Unpaid | Initial consultation / agreement
FEE-0002 | BUY-P0003 | BUY-C0003 | Phase 2 Engagement Fee | Fixed/Stage | BDT ______ |  |  | BDT ______ | BDT ______ | Partial/Unpaid | Phase 2 activation
FEE-0003 | BUY-P0005 | BUY-C0005 | Success Fee / Commission | % of purchase value | ____% |  |  | BDT 0 | TBC | Not Due | Purchase completion / settlement / registration
FEE-0004 | BUY-P0005 | BUY-C0005 | Third-Party Expense | Actual cost | BDT ______ |  |  | BDT 0 | BDT ______ | Unpaid | Legal/valuation/survey coordination | Buyer responsible

## Communication Log
Log ID | Date | Project ID | Buyer ID | Related Property Ref | Communication With | Channel | Summary | Action Required | Responsible | Due Date | Status
COM-0001 |  | BUY-P0001 | BUY-C0001 |  | Buyer | Phone | Initial purchase enquiry received | Schedule consultation | Buyer Support Coordinator |  | Open
COM-0002 |  | BUY-P0004 | BUY-C0004 | PROP-004 | Seller/Agent | WhatsApp | Property inspection availability discussed | Confirm inspection date | Coordinator |  | Open
COM-0003 |  | BUY-P0005 | BUY-C0005 | PROP-005 | Buyer | Email/WhatsApp | Offer amount discussion started | Collect written offer approval | Coordinator |  | Open
COM-0004 |  | BUY-P0003 | BUY-C0003 | PROP-003 | Lawyer/Surveyor | Phone | Land verification requirements discussed | Collect documents before review | Coordinator |  | Open

## Stage Gate Checklist
Gate ID | Project ID | Stage | Gate Question | Required Before Proceeding? | Current Status | Evidence Required | Decision | Approved By | Notes
GATE-001 | BUY-P0001 | Phase 1 Start | Has buyer profile and KYC been captured? | Yes | Pending | Buyer Master + KYC documents | Hold
GATE-002 | BUY-P0001 | Phase 2 Start | Has agreement been signed and Phase 1 fee paid? | Yes | Pending | Agreement + payment receipt | Hold
GATE-003 | BUY-P0004 | Inspection | Has property been shortlisted and buyer approved inspection? | Yes | Pending | Shortlist approval | Hold
GATE-004 | BUY-P0005 | Offer | Has inspection/document risk been disclosed to buyer? | Yes | Pending | Inspection + document summary | Hold
GATE-005 | BUY-P0005 | Transaction | Has buyer obtained/acknowledged independent legal/financial advice? | Yes | Pending | Advice record / acknowledgement | Hold
GATE-006 | BUY-P0005 | Settlement | Are fees, commission and approved expenses recorded? | Yes | Pending | Fee register | Hold

## Project Register
Project ID | Buyer ID | Buyer Name | Project Stage | Current Property Ref | Assigned Officer | Start Date | Target Completion | Progress % | Health/Risk | Latest Update | Next Action | Status
BUY-P0001 | BUY-C0001 | Sample Buyer - Personal Residence | Phase 1 Consultation |  | Buyer Support Coordinator |  |  | 10% | Medium | New enquiry received | Schedule consultation | Open
BUY-P0002 | BUY-C0002 | Sample NRB Buyer | Consultation / Requirement |  | Buyer Support Coordinator |  |  | 15% | Medium | Remote requirements being collected | Confirm local contact | Open
BUY-P0003 | BUY-C0003 | Sample Investor | Phase 2 Ready | PROP-003 | Residential Services Manager |  |  | 35% | High | Land property identified | Collect documents | Open
BUY-P0004 | BUY-C0004 | Sample Family Buyer | Inspection | PROP-004 | Buyer Support Coordinator |  |  | 45% | Medium | Property shortlisted | Schedule inspection | Open
BUY-P0005 | BUY-C0005 | Sample Furnished Property Buyer | Offer Stage | PROP-005 | Buyer Support Coordinator |  |  | 60% | Medium | Offer discussion active | Collect written offer approval | Open

## Post Purchase Services
Upsell ID | Project ID | Buyer ID | Service Option | Recommended? | Reason | Status | Assigned Division | Notes
UP-0001 | BUY-P0005 | BUY-C0005 | Property Care Cleaning | Yes | Move-in cleaning before occupation | Proposed | Property Care & Maintenance
UP-0002 | BUY-P0005 | BUY-C0005 | Utility Setup Coordination | Yes | New owner utility transfer | Proposed | Utility Coordination
UP-0003 | BUY-P0005 | BUY-C0005 | Smart Lock / CCTV | Optional | Security upgrade after purchase | Future | Smart Property Solutions
UP-0004 | BUY-P0002 | BUY-C0002 | NRB Property Monitoring | Yes | NRB investment property monitoring | Proposed | NRB Property Services
UP-0005 | BUY-P0004 | BUY-C0004 | Interior Consultation | Optional | Family move-in preparation | Future | Interior Design
UP-0006 | BUY-P0003 | BUY-C0003 | Leasing & Tenancy Management | Optional | Investment property rental income | Future | Leasing & Tenancy

## Project Closure Checklist
Closure ID | Project ID | Buyer ID | Closure Type | Checklist Item | Required? | Status | Evidence | Responsible | Notes
CL-001 | BUY-P0005 | BUY-C0005 | Completed Purchase | Final payment/commission received | Yes | Pending | Receipt | Accounts
CL-002 | BUY-P0005 | BUY-C0005 | Completed Purchase | Final report issued | Yes | Pending | Final report | Coordinator
CL-003 | BUY-P0005 | BUY-C0005 | Completed Purchase | Registration/settlement status recorded | Yes | Pending | Registration record / lawyer confirmation | Coordinator
CL-004 | BUY-P0005 | BUY-C0005 | Completed Purchase | Handover confirmed | Yes | Pending | Keys/possession note | Coordinator
CL-005 | BUY-P0005 | BUY-C0005 | Completed Purchase | All documents archived | Yes | Pending | CRM file | Admin
CL-006 | BUY-P0005 | BUY-C0005 | Completed Purchase | Buyer feedback collected | Yes | Pending | Feedback form | Coordinator
CL-007 | BUY-P0003 | BUY-C0003 | No Purchase / Withdrawn | Completed work and expenses invoiced | Yes | Pending | Invoice | Accounts | If buyer withdraws
CL-008 | BUY-P0003 | BUY-C0003 | No Purchase / Withdrawn | Protected introductions retained | Yes | Pending | Protected register | Coordinator | Non-circumvention survives

## KPI Dashboard Data
KPI | Target | Current Value | Data Source | Responsible | Review Frequency | Notes
Lead response time | Within 1 business day |  | Buyer Master Register | Buyer Support Coordinator | Weekly
Phase 1 consultation completion | Within 3 business days |  | Consultation Register | Buyer Support Coordinator | Weekly
Agreement signed before Phase 2 | 100% |  | Agreement Register | Manager | Weekly
Property shortlist prepared | Within 7-14 days where feasible |  | Property Shortlist | Coordinator | Weekly | Depends on buyer criteria
Inspection completion rate | 90%+ scheduled inspections completed |  | Inspection Schedule | Coordinator | Weekly
Document checklist completion | 100% before offer where applicable |  | Document Verification Register | Coordinator | Weekly
Professional advice coordination | As required before transaction |  | Professional Advice Tracker | Coordinator | Weekly
Offer approval evidence | 100% before offer submission |  | Offer Approval Checklist | Coordinator | Weekly
Circumvention incidents | 0 |  | Protected Introduction Register | Manager | Monthly
Successful purchase conversion | Track monthly |  | Project Register | Manager | Monthly
Average time to purchase | Track monthly |  | Project Register | Manager | Monthly
Commission/service fee recovery | 100% of due fees |  | Fees & Commission Register | Accounts | Monthly
Client satisfaction | 90%+ |  | Project Closure Checklist | Manager | Monthly

## Renetech CRM Mapping
CRM Module | Required Fields / Features | Workflow Trigger | Automation Requirement | User Role | Priority | Notes
Buyer Lead Management | Buyer name, contact, source, preferred location, budget, property type | New enquiry submitted | Auto-create Buyer ID and Project ID | Sales/Admin | High
Buyer Requirement Form | Property type, purpose, finance source, budget, must-have criteria | Consultation booked | Guided data collection form | Buyer Support Coordinator | High
Agreement Management | Agreement sent, signed date, exclusive period, service fee type | Phase 2 activation | E-sign and expiry reminders | Manager/Admin | High
Property Sourcing | Property source, seller/agent, asking price, availability, criteria match | Buyer criteria confirmed | Shortlist generator | Coordinator | High
Inspection Management | Inspection date, mode, checklist, photos, videos, report | Shortlist approval | Inspection reminder and mobile upload | Coordinator/Inspector | High
Document Verification | Document status, risk, professional advice, action items | Property shortlisted | Document checklist and risk flags | Coordinator | High
Protected Introduction | Seller/property introduction date, protected until, direct communication restriction | Property introduced | Auto protection period calculation | Manager | High
Negotiation Tracker | Offer, counter offer, approvals, status, evidence | Offer stage | Approval workflow before offer submission | Coordinator | High
Settlement Tracker | Agreement, deposit, registration, possession, handover | Offer accepted | Settlement task reminders | Coordinator | Medium
Finance Module | Phase fees, commission, expenses, invoices, outstanding | Invoice issued / transaction stage | Payment reminders and fee dashboard | Accounts | High
Risk Register | Risk rating, mitigation, owner, status | Any risk flagged | Escalation alerts for high/critical risk | Manager | High
Closure Module | Outcome, final payment, documents archived, feedback | Project completed/withdrawn | Closure checklist | Admin/Coordinator | Medium