## Dashboard
SEVENTH SKY PROPERTY CARE - SOLAR & ENERGY SOLUTIONS CRM BLUEPRINT V2.0
Purpose | Detailed CRM workbook for Solar & Energy Solutions: client lifecycle, provider management, work orders, installation, maintenance, battery/backup, warranty and financial controls.
Built From | Customer Service Agreement, Project Work Order, Service Provider Master Agreement, Client SOP and Third-Party Provider SOP.
Client Workflow | Lead → Consultation → Needs Assessment → Site Assessment → Proposal & Quotation → Agreement → Deposit → Provider Assignment → Project Delivery → Testing & Handover → Warranty → Support.
Provider Workflow | Provider enquiry → Compliance review → Insurance verification → Master agreement signing → Provider approval → Work order assignment → Project delivery → Performance review.
Key Legal Controls | No guarantee of energy savings/output/ROI; third-party delivery; manufacturer warranties; provider indemnity; Cumilla exclusivity; non-circumvention; protected client period.
Core Automations for RENETECH | Auto IDs, lead reminders, site assessment booking, dynamic quotation, agreement generation, work order generation, procurement tracking, warranty expiry reminders, AMC reminders.
Dashboards Required | Executive, Sales Pipeline, Operations, Procurement, Installation, Maintenance, Provider Compliance, Warranty, Finance, Risk & Incident.
Editable By | Seventh Sky admin team and authorised CRM users only.
Version | V2.0 - populated enterprise template
Status | Ready for RENETECH CRM design discussion.
Important | Use this workbook as a system blueprint; sample rows are examples and should be replaced with live CRM data once operational.
Planned Go-Live | November 2026
Business Unit | Seventh Sky Solar & Energy Solutions
Brand | Seventh Sky Property Care

## Lists & Status Values
List Type | Value | Use In CRM | Notes
Lead Status | New Lead | Client Master Register | Initial enquiry captured
Lead Status | Contacted | Client Master Register | Client contacted by consultant
Lead Status | Consultation Completed | Needs Assessment | Client goals and electricity usage captured
Lead Status | Site Assessment Scheduled | Site Assessment | Roof/electrical/shading assessment arranged
Lead Status | Proposal Drafting | Proposal Register | Technical proposal under preparation
Lead Status | Quotation Issued | Quotation Register | Client has received written quote
Lead Status | Agreement Sent | Agreement Register | Customer service agreement sent
Lead Status | Agreement Signed | Agreement Register | Signed before project starts
Lead Status | Deposit Received | Payment Register | Deposit paid before procurement where applicable
Project Status | Procurement | Procurement Register | Equipment ordered or being sourced
Project Status | Installation Scheduled | Installation Register | Provider scheduled
Project Status | Installation In Progress | Installation Register | On-site work underway
Project Status | Testing & Commissioning | Commissioning Register | System testing and commissioning
Project Status | Handover | Handover Register | User manuals/warranties provided
Project Status | Completed | Project Register | Practical completion achieved
Project Status | Closed | Project Closure Register | All documentation/payment/feedback completed
Project Status | Suspended | Project Register | Payment, safety, access or compliance issue
Priority | Low | Tasks / Complaints | Routine
Priority | Medium | Tasks / Complaints | Needs follow-up
Priority | High | Tasks / Complaints | Urgent
Priority | Critical | Incident Register | Safety/fire/electrical/battery risk
Service Category | Solar System Consultation | Service Request | Site assessment, feasibility, energy usage, recommendations
Service Category | Residential Solar Installation | Service Request | Solar panel, inverter, electrical integration, commissioning
Service Category | Solar Battery Solutions | Service Request | Battery assessment, supply, install, integration
Service Category | Residential Solar Upgrades | Service Request | System expansion, inverter upgrade, battery expansion, optimisation
Service Category | Preventive Maintenance | Maintenance Register | Panel cleaning, inspection, monitoring
Service Category | Corrective Maintenance | Repair Register | Fault diagnosis, inverter repair, wiring repair, component replacement
Service Category | Performance Optimisation | Performance Register | Health check, output analysis, energy efficiency review
Service Category | Battery & Backup Power | Battery Register | Home battery, UPS, emergency power
Provider Status | Pending Onboarding | Provider Master Register | Application received
Provider Status | Conditional Approval | Provider Master Register | Can work only after documents completed
Provider Status | Approved | Provider Master Register | Eligible for work order
Provider Status | Suspended | Provider Master Register | No new work order
Provider Status | Terminated | Provider Master Register | Inactive

## Client Master Register
Client ID | Project ID | Client Name | Client Type | Mobile | Email | NID/Passport/Company Reg | Property Address | District | Property Type | Lead Source | Requested Service | Current Status | Assigned Consultant | Next Action | Next Follow-Up Date | Notes
SES-C0001 | SES-P0001 | Sample Residential Owner | Residential | 01XXXXXXXXX | client@example.com | NID pending | Cumilla Sadar, Cumilla | Cumilla | House | Website | Residential Solar Installation | New Lead | Solar Consultant | Call client and collect electricity bill |  | Example only
SES-C0002 | SES-P0002 | Sample NRB Property Owner | Residential/NRB | 01XXXXXXXXX | nrb@example.com | Passport pending | Kandirpar, Cumilla | Cumilla | House | Referral | Solar Battery Solutions + Remote Monitoring | Consultation Completed | Solar Consultant | Arrange site assessment with caretaker |  | Example only
SES-C0003 | SES-P0003 | Sample Small Business | Commercial | 01XXXXXXXXX | business@example.com | Trade licence pending | Dhaka | Dhaka | Commercial Building | Direct Call | System Health Check + Output Analysis | Site Assessment Scheduled | Project Coordinator | Assign provider for site assessment |  | Example only
SES-C0004 | SES-P0004 | Sample Homeowner | Residential | 01XXXXXXXXX | home@example.com | NID pending | Cumilla | Cumilla | House | Facebook | Inverter Upgrade + Battery Expansion | Quotation Issued | Solar Consultant | Follow up quote approval |  | Example only

## Client Needs Assessment
Assessment ID | Client ID | Project ID | Client Goal | Average Monthly Bill | Peak Usage | Existing Solar? | Existing System Capacity | Backup Need | Budget Range | Preferred Outcome | Financing Interest | Documents Needed | Recommended Next Step | Remarks
NA-0001 | SES-C0001 | SES-P0001 | Reduce electricity cost and improve energy reliability | BDT 8,000 | Evening use | No |  | Basic backup optional | BDT 200,000-300,000 | Solar installation | Yes | Electricity bills, roof photos, NID | Schedule roof and shading assessment
NA-0002 | SES-C0002 | SES-P0002 | Remote property power backup and monitoring | BDT 10,000 | Night and pump use | No |  | Battery backup required | BDT 350,000+ | Solar + battery | No | Caretaker approval, bill copies, property access | Remote site assessment with caretaker | NRB owner
NA-0003 | SES-C0003 | SES-P0003 | Check underperformance of existing system | BDT 25,000 | Business hours | Yes | 5kW | No | BDT 20,000-50,000 | Performance optimisation | No | Existing system details, inverter model | System health check
NA-0004 | SES-C0004 | SES-P0004 | Expand battery backup and improve inverter efficiency | BDT 12,000 | Evening + outage | Yes | 3kW | High | BDT 150,000-250,000 | Inverter upgrade + battery expansion | Maybe | Existing equipment photos | Prepare upgrade quote

## Service Request Register
Request ID | Request Date | Client ID | Project ID | Service Category | Specific Service | Priority | Preferred Date | Site Visit Required | Customer Agreement Required | Deposit Required | Assigned Provider ID | Request Status | Remarks
SR-0001 |  | SES-C0001 | SES-P0001 | Residential Solar Installation | Solar panel and inverter installation | Medium |  | Yes | Yes | Yes |  | New | Collect electricity bill
SR-0002 |  | SES-C0002 | SES-P0002 | Solar Battery Solutions | Home battery storage + remote monitoring | High |  | Yes | Yes | Yes |  | Consultation Completed | Caretaker access required
SR-0003 |  | SES-C0003 | SES-P0003 | Performance Optimisation | System health check + output analysis | High |  | Yes | Yes | No |  | Assessment Scheduled | Business site
SR-0004 |  | SES-C0004 | SES-P0004 | Residential Solar Upgrades | Inverter upgrade + battery expansion | Medium |  | Yes | Yes | Yes |  | Quoted | Subject to equipment availability

## Energy Usage Register
Energy ID | Client ID | Project ID | Bill Period | Monthly Bill BDT | Estimated kWh | Peak Usage Time | Appliances / Loads | Backup Critical Loads | Notes | Uploaded Bill Link
EU-0001 | SES-C0001 | SES-P0001 | Last 3 months average | 8000 |  | Evening | Lights, fans, fridge, pump | Lights, fridge, Wi-Fi | Use for system sizing
EU-0002 | SES-C0002 | SES-P0002 | Last 6 months average | 10000 |  | Night | Security, pump, lights | Security, pump, lights | NRB property monitoring needed
EU-0003 | SES-C0003 | SES-P0003 | Last month | 25000 |  | Business hours | Office equipment, lighting, AC | Minimal | Performance review needed

## Property & Site Register
Site ID | Client ID | Project ID | Property Type | Roof Type | Roof Condition | Roof Access | Roof Orientation | Shading Risk | Electrical Access | Switchboard Condition | Battery Location | Safety Risk | Recommended Assessment | Status
SITE-0001 | SES-C0001 | SES-P0001 | House | Concrete/RCC | To be checked | Stair/roof access | South/unknown | Unknown | Available | To be checked | Utility room possible | Medium | Roof + electrical + shading assessment | Planned
SITE-0002 | SES-C0002 | SES-P0002 | House | Concrete/RCC | To be checked | Caretaker access | Unknown | Medium | Available | To be checked | Ventilated secure space needed | Medium | Battery placement + fire safety review | Planned
SITE-0003 | SES-C0003 | SES-P0003 | Commercial Building | Existing system | To be checked | Available | Unknown | Unknown | Available | Existing solar DB | N/A | High | Performance + safety review | Scheduled

## Solar Site Assessment
Assessment ID | Project ID | Client ID | Provider ID | Assessment Date | Roof Suitable? | Structural Review | Shading Assessment | Orientation | Inverter Location | Battery Placement | Electrical Capacity | Photos Collected | Recommendation | Variation Risk | Assessment Status
SA-0001 | SES-P0001 | SES-C0001 |  |  | To be checked | Required | Required | Unknown | To be identified | Optional | To be checked | Pending | Residential solar installation feasibility | Medium | Planned
SA-0002 | SES-P0002 | SES-C0002 |  |  | To be checked | Required | Required | Unknown | To be identified | Required - ventilation/fire safety | To be checked | Pending | Solar + battery feasibility | High | Planned
SA-0003 | SES-P0003 | SES-C0003 |  |  | Existing system | Visual review | Required | Unknown | Existing | N/A | To be checked | Pending | System health check and output analysis | Medium | Scheduled

## Technical Proposal Register
Proposal ID | Project ID | Client ID | Provider ID | System Size Proposed | Panel Type | Inverter Type | Battery Type | Estimated Output | Backup Capacity | Warranty Summary | Proposal Date | Proposal Status | Technical Notes
TP-0001 | SES-P0001 | SES-C0001 | SP-001 | 5kW | Tier-1 panel TBC | Hybrid/string inverter TBC | Optional | Subject to assessment | Optional | Manufacturer + workmanship warranty |  | Draft | System size to be finalised after roof assessment
TP-0002 | SES-P0002 | SES-C0002 | SP-002 | 5kW + battery | Tier-1 panel TBC | Hybrid inverter | Lithium battery TBC | Subject to assessment | Essential loads backup | Manufacturer + installer warranty |  | Draft | Battery ventilation and safety required
TP-0003 | SES-P0003 | SES-C0003 | SP-003 | Existing 5kW review | Existing | Existing inverter | N/A | Output analysis required | N/A | Service warranty |  | Pending Assessment | Performance data required

## Quotation Register
Quote No | Project ID | Client ID | Service Description | Seventh Sky Fee | Provider Fee | Equipment Cost | Labour Cost | Transport | Government/Permit | Insurance | Other Cost | Total Quote | Validity | Issued Date | Client Decision | Approved Date | Notes
Q-0001 | SES-P0001 | SES-C0001 | Residential solar installation - proposed 5kW system | BDT 20,000 | BDT 60,000 | BDT 260,000 | BDT 30,000 | BDT 5,000 | BDT 0 | BDT 0 | BDT 0 | BDT 375,000 | 30 days |  | Pending |  | Subject to supplier pricing
Q-0002 | SES-P0002 | SES-C0002 | Solar battery solution with remote monitoring | BDT 25,000 | BDT 75,000 | BDT 420,000 | BDT 40,000 | BDT 8,000 | BDT 0 | BDT 0 | BDT 0 | BDT 568,000 | 30 days |  | Pending |  | Battery model to be confirmed
Q-0003 | SES-P0003 | SES-C0003 | System health check, output analysis and efficiency review | BDT 7,000 | BDT 18,000 | BDT 0 | BDT 0 | BDT 2,000 | BDT 0 | BDT 0 | BDT 0 | BDT 27,000 | 14 days |  | Pending |  | Maintenance service

## Customer Agreement Register
Agreement ID | Project ID | Client ID | Agreement Type | Selected Services | Agreement Sent Date | Signed Date | Project Value | Payment Structure | Agreement Status | Storage Link | Remarks
CSA-0001 | SES-P0001 | SES-C0001 | Customer Service Agreement | Residential solar installation |  |  | BDT 375,000 | Deposit/progress/final | Draft |  | No procurement before deposit
CSA-0002 | SES-P0002 | SES-C0002 | Customer Service Agreement | Solar battery + backup power |  |  | BDT 568,000 | Deposit/progress/final | Draft |  | Battery terms to be clear
CSA-0003 | SES-P0003 | SES-C0003 | Customer Service Agreement | System health check + output analysis |  |  | BDT 27,000 | 100% on completion / as agreed | Draft |  | Maintenance project

## Deposit & Approval Register
Approval ID | Project ID | Client ID | Quotation Approved? | Agreement Signed? | Deposit Required? | Deposit Amount | Deposit Received? | Approval Date | Procurement Approved? | Approved By | Remarks
AP-0001 | SES-P0001 | SES-C0001 | No | No | Yes | BDT 112,500 | No |  | No |  | 30% example
AP-0002 | SES-P0002 | SES-C0002 | No | No | Yes | BDT 170,400 | No |  | No |  | 30% example
AP-0003 | SES-P0003 | SES-C0003 | No | No | No | BDT 0 | N/A |  | No |  | Service-only project

## Work Order Register
WO No | Project ID | Client ID | Provider ID | Service Category | Scope Summary | Issue Date | Accepted Date | Start Date | Target Completion | Work Order Status | Provider Fee | Seventh Sky Fee | Warranty Required | Reports Required | Special Conditions
WO-0001 | SES-P0001 | SES-C0001 | SP-001 | Residential Solar Installation | Install solar panels, inverter, wiring, test and commission system |  |  |  |  | Draft | BDT 60,000 | BDT 20,000 | Manufacturer + workmanship | Site, installation, testing, commissioning reports | Cumilla exclusivity applies
WO-0002 | SES-P0002 | SES-C0002 | SP-002 | Solar Battery Solutions | Supply/install/integrate battery with hybrid inverter and monitoring |  |  |  |  | Draft | BDT 75,000 | BDT 25,000 | Battery + workmanship | Battery placement, commissioning, handover reports | Fire/ventilation assessment required
WO-0003 | SES-P0003 | SES-C0003 | SP-003 | Performance Optimisation | Conduct health check, output analysis and efficiency recommendations |  |  |  |  | Draft | BDT 18,000 | BDT 7,000 | Service warranty | Health check and output report | Commercial site

## Procurement Register
Procurement ID | Project ID | Client ID | Item Category | Item Description | Supplier | Brand/Model | Quantity | Unit Cost | Total Cost | Order Date | Expected Delivery | Delivery Status | Payment Status | Notes
PROC-0001 | SES-P0001 | SES-C0001 | Solar Panels | Tier-1 panels TBC | Supplier TBC | TBC | 10 |  |  |  |  | Not Ordered | Not Paid | No procurement before deposit
PROC-0002 | SES-P0001 | SES-C0001 | Inverter | Hybrid/string inverter TBC | Supplier TBC | TBC | 1 |  |  |  |  | Not Ordered | Not Paid
PROC-0003 | SES-P0002 | SES-C0002 | Battery | Lithium battery system TBC | Supplier TBC | TBC | 1 |  |  |  |  | Not Ordered | Not Paid | Check warranty
PROC-0004 | SES-P0002 | SES-C0002 | Monitoring System | Remote monitoring device/app | Supplier TBC | TBC | 1 |  |  |  |  | Not Ordered | Not Paid

## Installation Project Register
Installation ID | Project ID | Client ID | Provider ID | System Size | Panels | Inverter | Battery | Mounting System | Start Date | Completion Date | Testing Done | Commissioning Done | Handover Done | Installation Status | Warranty Expiry
INST-0001 | SES-P0001 | SES-C0001 | SP-001 | 5kW proposed | TBC | TBC | Optional | TBC |  |  | No | No | No | Not Started
INST-0002 | SES-P0002 | SES-C0002 | SP-002 | 5kW + battery proposed | TBC | Hybrid TBC | TBC | TBC |  |  | No | No | No | Not Started

## Testing & Commissioning
Commissioning ID | Project ID | Client ID | Provider ID | Testing Date | Electrical Safety Check | Inverter Test | Battery Test | Monitoring Test | Grid/Load Test | Issue Found | Rectification Required | Commissioning Report | Status
COM-0001 | SES-P0001 | SES-C0001 | SP-001 |  | Pending | Pending | N/A/Optional | Pending | Pending | Unknown | Unknown |  | Planned
COM-0002 | SES-P0002 | SES-C0002 | SP-002 |  | Pending | Pending | Pending | Pending | Pending | Unknown | Unknown |  | Planned

## Battery & Backup Register
Battery ID | Project ID | Client ID | Battery Type | Capacity | Backup Loads | UPS Integration? | Emergency Power Requirement | Ventilation Checked | Fire Safety Checked | Installation Status | Warranty | Notes
BAT-0001 | SES-P0002 | SES-C0002 | Lithium TBC | TBC | Lights, Wi-Fi, security, pump | Optional | Yes | Pending | Pending | Not Started | Manufacturer warranty TBC | Battery location required
BAT-0002 | SES-P0001 | SES-C0001 | Optional | Optional | Fridge, lights | No | Optional | Pending | Pending | Not Started | TBC | Upsell option

## Maintenance Register
Maintenance ID | Project ID | Client ID | Service Type | Panel Cleaning | System Inspection | Performance Monitoring | Service Date | Next Due Date | Provider ID | Findings | Status | Recommendations
MNT-0001 | SES-P0003 | SES-C0003 | System Health Check | No | Yes | Yes |  |  | SP-003 | Pending assessment | Scheduled | Output analysis required
MNT-0002 | SES-P0001 | SES-C0001 | Preventive Maintenance | Yes | Yes | Optional |  |  | SP-001 | To be scheduled after installation | Future | Offer annual maintenance

## Repair & Fault Register
Repair ID | Project ID | Client ID | Fault Type | Diagnosis | Parts Required | Estimated Cost | Repair Action | Provider ID | Completion Date | Warranty | Status | Remarks
REP-0001 | SES-P0003 | SES-C0003 | Low output | Pending diagnosis | Unknown | TBC | Health check first | SP-003 |  | Service warranty TBC | Open | Existing system
REP-0002 | SES-P0004 | SES-C0004 | Inverter issue | Pending assessment | Inverter TBC | TBC | Inverter upgrade quote | SP-001 |  | Manufacturer + workmanship | Quoted | Upgrade project

## Performance Monitoring
Performance ID | Project ID | Client ID | Monitoring Date | Expected Output | Actual Output | Variance | Weather/Shading Notes | Issue Identified | Recommended Action | Provider ID | Status
PERF-0001 | SES-P0003 | SES-C0003 |  | TBC | TBC | TBC | Shading to assess | Unknown | Output analysis required | SP-003 | Planned
PERF-0002 | SES-P0001 | SES-C0001 |  | TBC | TBC | TBC | After installation | Unknown | Set baseline after commissioning | SP-001 | Future

## Warranty Register
Warranty ID | Project ID | Client ID | Provider ID | Warranty Type | Item/Service | Start Date | Expiry Date | Coverage | Exclusions | Claim Process | Warranty Status
WAR-0001 | SES-P0001 | SES-C0001 | SP-001 | Manufacturer | Solar panels/inverter TBC |  |  | Manufacturer defects subject to terms | Misuse, storm, unauthorised modification | Notify Seventh Sky in writing | Pending
WAR-0002 | SES-P0001 | SES-C0001 | SP-001 | Workmanship | Installation workmanship |  |  | Installation defects | Client misuse/third-party work excluded | Inspection and rectification if valid | Pending
WAR-0003 | SES-P0002 | SES-C0002 | SP-002 | Manufacturer | Battery system TBC |  |  | Battery warranty subject to manufacturer terms | Improper use, environment, unauthorised modification | Notify Seventh Sky | Pending

## Recovered_Sheet1
AMC ID | Client ID | Project ID | Package Type | Frequency | Start Date | End Date | Last Visit | Next Visit | Provider ID | Renewal Reminder | AMC Status | Inclusions
AMC-0001 | SES-C0001 | SES-P0001 | Residential Solar Preventive Maintenance | Annual |  |  |  |  | SP-001 |  | Proposed | Panel cleaning, inspection, monitoring review
AMC-0002 | SES-C0002 | SES-P0002 | Battery & Backup Support Plan | Six-Monthly |  |  |  |  | SP-002 |  | Proposed | Battery health check, backup test, monitoring review
AMC-0003 | SES-C0003 | SES-P0003 | Commercial System Health Plan | Quarterly |  |  |  |  | SP-003 |  | Proposed | Performance monitoring, system inspection, report

## Invoice & Payment Register
Invoice No | Project ID | Client ID | Invoice Type | Invoice Amount | Due Date | Paid Amount | Outstanding Amount | Payment Status | Provider Payout Status | Receipt Link | Remarks
INV-0001 | SES-P0001 | SES-C0001 | Deposit | BDT 112,500 |  | BDT 0 | BDT 112,500 | Unpaid | Not Due |  | 30% deposit example
INV-0002 | SES-P0001 | SES-C0001 | Progress Payment | BDT 150,000 |  | BDT 0 | BDT 150,000 | Unpaid | Not Due |  | Upon equipment delivery
INV-0003 | SES-P0001 | SES-C0001 | Final Payment | BDT 112,500 |  | BDT 0 | BDT 112,500 | Unpaid | Not Due |  | Upon practical completion
INV-0004 | SES-P0003 | SES-C0003 | Maintenance Service | BDT 27,000 |  | BDT 0 | BDT 27,000 | Unpaid | Not Due |  | Service project

## Client Workflow Detailed
Phase | Step No | Workflow Step | Detailed Activity | Responsible | CRM Record | Required Evidence | Client Approval Required | Automation Opportunity | Output
Lead Management | 1 | Capture Lead | Collect name, mobile, email, property address, property type and service required. | Solar Consultant | Client Master Register | Lead form | No | Auto-create Client ID and Project ID | Lead created
Consultation | 2 | Initial Consultation | Discuss goals, current electricity usage, existing solar, budget and expected outcomes. | Solar Consultant | Client Needs Assessment | Consultation notes | Yes | Guided questionnaire | Needs identified
Energy Assessment | 3 | Review Electricity Usage | Review electricity bills, usage patterns, peak consumption and backup requirements. | Solar Consultant | Energy Usage Register | Bill copies | Yes | Bill upload reminder | Energy profile created
Site Assessment | 4 | Arrange Assessment | Schedule roof, structural, electrical, shading and battery placement assessment. | Project Coordinator | Solar Site Assessment | Booking record | Yes | Auto-reminder to client/provider | Assessment booked
Technical Proposal | 5 | Obtain Provider Proposal | Coordinate with approved provider for system size, equipment, expected generation and warranty information. | Project Coordinator | Technical Proposal Register | Technical proposal | No | Provider portal upload | Proposal received
Quotation | 6 | Prepare Quotation | Include equipment, installation, coordination fees, optional insurance and maintenance plan. | Solar Consultant / Accounts | Quotation Register | Quotation | Yes | Auto-populate quote from proposal | Quotation issued
Agreement | 7 | Execute Agreement | Send and collect Solar & Energy Solutions Customer Service Agreement before work begins. | Management | Customer Agreement Register | Signed agreement | Yes | E-sign workflow | Agreement signed
Deposit | 8 | Collect Deposit | Collect deposit and required approvals before procurement or installation. | Accounts | Deposit & Approval Register | Receipt | Yes | Payment reminder | Procurement approved
Provider Assignment | 9 | Issue Work Order | Assign approved provider and issue work order with scope, timeline, pricing and reporting requirements. | Project Coordinator | Work Order Register | Work Order | No | Auto-generate work order | Provider assigned
Procurement | 10 | Procure Equipment | Track panels, inverter, batteries, monitoring and electrical components. | Project Coordinator | Procurement Register | Supplier invoices/delivery note | Client approval if substitutions | Procurement tracker | Equipment ready
Installation | 11 | Monitor Delivery | Track installation progress, site attendance, delays, safety incidents and variations. | Operations Manager | Installation Project Register | Progress photos/reports | Variation approval if needed | Progress status updates | Installation completed
Testing | 12 | Commissioning | Verify system operational, testing completed, safety checks completed and commissioning report issued. | Provider / Operations | Testing & Commissioning | Commissioning report | Yes | Completion checklist | System commissioned
Handover | 13 | Client Handover | Provide warranty documents, manuals, maintenance recommendations and emergency contacts. | Project Coordinator | Handover Register / Warranty Register | Handover pack | Yes | Auto handover pack | Client handover complete
After-Sales | 14 | Warranty & Maintenance | Coordinate warranty claims, service requests, equipment issues, cleaning and inspection schedule. | Coordinator | Warranty / AMC Register | Warranty/AMC record | No | Auto warranty and AMC reminders | After-sales support active
Closure | 15 | Project Closure | Collect final payment, client satisfaction survey, close checklist and archive files. | Accounts / Coordinator | Project Closure Register | Payment receipt and survey | No | Auto closure checklist | Project closed

## Client Service Checklist
Checklist ID | Project ID | Stage | Checklist Item | Mandatory? | Responsible | Evidence Required | Related CRM Sheet | Status | Notes
CSC-001 | SES-P0001 | Lead | Client contact details captured | Yes | Solar Consultant | Lead form | Client Master Register | Pending
CSC-002 | SES-P0001 | Consultation | Client goals and budget recorded | Yes | Solar Consultant | Needs notes | Client Needs Assessment | Pending
CSC-003 | SES-P0001 | Energy Assessment | Electricity bill collected | Yes | Solar Consultant | Bill copy | Energy Usage Register | Pending
CSC-004 | SES-P0001 | Site Assessment | Roof/electrical/shading assessment completed | Yes | Provider | Assessment report/photos | Solar Site Assessment | Pending
CSC-005 | SES-P0001 | Proposal | Technical proposal obtained | Yes | Project Coordinator | Provider proposal | Technical Proposal Register | Pending
CSC-006 | SES-P0001 | Quotation | Written quotation issued | Yes | Accounts | Quotation | Quotation Register | Pending
CSC-007 | SES-P0001 | Agreement | Customer service agreement signed | Yes | Management | Signed agreement | Agreement Register | Pending | No work before signing
CSC-008 | SES-P0001 | Deposit | Deposit received before procurement | If required | Accounts | Receipt | Payment Register | Pending
CSC-009 | SES-P0001 | Work Order | Provider work order issued and accepted | Yes | Project Coordinator | Accepted work order | Work Order Register | Pending
CSC-010 | SES-P0001 | Procurement | Equipment procurement approved and tracked | If installation | Project Coordinator | Supplier record | Procurement Register | Pending
CSC-011 | SES-P0001 | Installation | Before/during/after photos uploaded | Yes | Provider | Photos | Installation Register | Pending
CSC-012 | SES-P0001 | Commissioning | Testing and commissioning completed | Yes | Provider | Commissioning report | Testing & Commissioning | Pending
CSC-013 | SES-P0001 | Warranty | Warranty documents recorded | Yes | Coordinator | Warranty certificates | Warranty Register | Pending
CSC-014 | SES-P0001 | Handover | User manuals and maintenance advice provided | Yes | Coordinator | Handover record | Project Register | Pending
CSC-015 | SES-P0001 | Closure | Feedback collected and project closed | Yes | Coordinator | Feedback survey | Project Closure Register | Pending

## Provider Master Register
Provider ID | Business Name | Contact Person | Mobile | Email | Trade Licence | TIN | BIN | Approved Services | Coverage Area | Cumilla Exclusivity Signed | Master Agreement Status | Insurance Status | Provider Status | Assigned Manager | Notes
SP-001 | Sample Solar Installer Ltd | Provider Contact | 01XXXXXXXXX | provider@example.com | Pending | Pending | Pending | Solar installation, inverter, maintenance | Dhaka/Cumilla through Seventh Sky | Yes | Active | Verified | Approved | Provider Relationship Manager | Example only
SP-002 | Sample Battery Backup Services | Provider Contact | 01XXXXXXXXX | battery@example.com | Pending | Pending | Pending | Battery, UPS, backup systems | Dhaka/Cumilla through Seventh Sky | Yes | Active | Pending | Conditional Approval | Provider Relationship Manager | Collect insurance before work
SP-003 | Sample Solar Maintenance Team | Provider Contact | 01XXXXXXXXX | maintenance@example.com | Pending | Pending | Pending | Panel cleaning, inspection, performance optimisation | Dhaka/Cumilla through Seventh Sky | Yes | Pending | Pending | Pending Onboarding | Provider Relationship Manager | Due diligence required

## Provider Compliance Register
Provider ID | Compliance Item | Required | Evidence Required | Issue Date | Expiry Date | Verified By | Verification Date | Compliance Status | Follow-Up Action
SP-001 | Trade Licence | Yes | Trade licence copy |  |  | Provider Relationship Manager |  | Pending | Collect before full approval
SP-001 | Company Registration | If company | Registration certificate |  |  | Provider Relationship Manager |  | Pending | Collect
SP-001 | TIN | Yes | TIN certificate |  |  | Accounts |  | Pending | Collect
SP-001 | BIN | If applicable | BIN certificate |  |  | Accounts |  | N/A | Confirm applicability
SP-001 | Electrical Licence | Yes for installation | Electrical licence/certificate |  |  | Operations Manager |  | Pending | Mandatory before installation work
SP-001 | Engineering Certification | If design/engineering | Engineer credentials |  |  | Operations Manager |  | Pending | Required for technical design
SP-001 | Renewable Energy Certification | Recommended | Solar training/certification |  |  | Operations Manager |  | Pending | Collect if available
SP-001 | Safety Training | Yes | OH&S/working at heights/electrical safety evidence |  |  | Operations Manager |  | Pending | Annual update required
SP-002 | Battery Safety Competency | Yes for battery | Battery installation/safety evidence |  |  | Operations Manager |  | Pending | Mandatory for battery work

## Provider Insurance Register
Provider ID | Insurance Type | Required? | Policy Number | Insurer | Coverage Amount | Expiry Date | Verified? | Reminder Date | Action Required
SP-001 | Public Liability | Yes |  |  | BDT ______ |  | No |  | Mandatory before work order
SP-001 | Professional Indemnity | If design/engineering |  |  | BDT ______ |  | No |  | Required if giving professional advice/design
SP-001 | Workers Compensation | If employees |  |  | BDT ______ |  | No |  | Confirm workforce structure
SP-001 | Employer Liability | If applicable |  |  | BDT ______ |  | No |  | Confirm applicability
SP-001 | Vehicle Insurance | If vehicles used |  |  | BDT ______ |  | No |  | Collect if transport used
SP-001 | Contractor Insurance | Yes |  |  | BDT ______ |  | No |  | Collect certificate
SP-002 | Product Liability | Recommended for equipment |  |  | BDT ______ |  | No |  | Recommended
SP-002 | Contractor All-Risk | Recommended installation |  |  | BDT ______ |  | No |  | Recommended for installation projects

## Provider Capability Matrix
Provider ID | Solar Consultation | Site Assessment | Energy Usage Analysis | Solar Installation | Inverter Installation | Battery Installation | UPS Integration | System Expansion | Inverter Upgrade | Battery Expansion | Panel Cleaning | System Inspection | Performance Monitoring | Fault Diagnosis | Inverter Repair | Wiring Repair | Component Replacement | Emergency Power | Commercial Projects | Emergency Call-Out
SP-001 | Yes | Yes | Yes | Yes | Yes | No | No | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes
SP-002 | Yes | Yes | Yes | No | Yes | Yes | Yes | No | Yes | Yes | No | Yes | Yes | Yes | No | No | Yes | Yes | Yes | Yes
SP-003 | Yes | Yes | Yes | No | No | No | No | No | No | No | Yes | Yes | Yes | Yes | No | Yes | Yes | No | Yes | No

## Cumilla Exclusivity Register
Provider ID | Provider Name | Cumilla Clause Signed | Briefing Date | Acknowledgement Evidence | Allowed to Work in Cumilla Independently? | Referral Obligation | Breach Risk | Monitoring Notes
SP-001 | Sample Solar Installer Ltd | Yes |  | Signed Master Agreement | No | All Cumilla enquiries must be referred to Seventh Sky | Low | Monitor marketing and direct client contacts
SP-002 | Sample Battery Backup Services | Yes |  | Signed Master Agreement | No | Must not quote/contract directly in Cumilla | Medium | Conditional approval until insurance complete
SP-003 | Sample Solar Maintenance Team | Pending |  | Pending Agreement | No | No direct Cumilla services | High | Do not assign Cumilla clients until signed

## Provider Workflow Detailed
Phase | Step No | Workflow Step | Detailed Activity | Responsible | CRM Record | Required Evidence | Approval/Decision | Automation Opportunity | Output
Provider Onboarding | 1 | Provider Enquiry/Application | Collect company profile, service capability, experience and service locations. | Provider Relationship Manager | Provider Master Register | Company profile | Proceed/Reject | Auto-create Provider ID | Provider profile created
Provider Onboarding | 2 | Capability Assessment | Assess whether provider can deliver consultation, installation, battery, maintenance, repair, monitoring and emergency services. | Operations Manager | Provider Capability Matrix | Capability checklist | Approve service categories | Dropdown capability matrix | Capability approved
Compliance | 3 | Compliance Verification | Verify trade licence, company registration, TIN, BIN, electrical licences, engineering and safety certifications. | Provider Relationship Manager | Provider Compliance Register | Licence/certificates | Compliant/Conditional/Reject | Expiry reminders | Compliance status recorded
Insurance | 4 | Insurance Verification | Verify public liability, professional indemnity, workers compensation, contractor and vehicle insurance. | Provider Relationship Manager | Provider Insurance Register | Insurance certificates | Approved/Not approved | Expiry reminders | Insurance status recorded
Contracting | 5 | Master Agreement Signing | Obtain signed Service Delivery Provider Master Agreement before any client assignment. | Management | Master Agreement Register | Signed agreement | Required before work | E-sign workflow | Provider legally onboarded
Territory Protection | 6 | Cumilla Exclusivity Briefing | Explain protected client, non-circumvention, referral obligation and no direct Cumilla market activity. | Management | Cumilla Exclusivity Register | Signed acknowledgement | Must be signed | Compliance reminder | Territory controls active
Project Assignment | 7 | Scope Review | Review client request, technical need, budget, location and risks before provider selection. | Project Coordinator | Service Request Register | Client request | Provider selection | Auto-match by capability/service area | Provider selected
Project Assignment | 8 | Work Order Issue | Prepare work order with client, project site, service category, scope, pricing, warranty and insurance requirements. | Project Coordinator | Work Order Register | Work Order | Provider acceptance | Auto-populate from CRM | Work order issued
Delivery | 9 | Site Assessment | Provider conducts roof, structural, shading, electrical, battery placement and safety review. | Provider | Solar Site Assessment | Site report/photos | Variation required? | Mobile upload | Site assessment completed
Delivery | 10 | Installation / Service Delivery | Provider performs installation, maintenance, repair, performance optimisation or battery/backup work. | Provider | Installation/Maintenance Register | Progress reports/photos | Quality review | Progress status updates | Work completed
Quality | 11 | Testing & Commissioning | Provider tests system, completes commissioning and submits reports/warranties/manuals. | Provider / Operations | Testing & Commissioning | Commissioning report | Completion approval | Completion checklist | System handed over
Warranty | 12 | Warranty Registration | Record manufacturer and workmanship warranties, warranty expiry dates and claim process. | Coordinator | Warranty Register | Warranty certificates | Ongoing tracking | Warranty reminders | Warranty active
Finance | 13 | Provider Payment | Check client payments, provider invoice, approved variations and payout status. | Accounts | Invoice & Payment Register | Invoice/receipt | Pay/Hold | Payment reminders | Provider paid
Performance | 14 | Provider KPI Review | Review completion rate, defect rate, warranty claims, client satisfaction and compliance status. | Operations Manager | Provider KPI Register | KPI data | Renew/Suspend/Terminate | KPI dashboard | Provider performance reviewed

## Provider Checklist
Checklist Category | Checklist Item | Mandatory? | Frequency | Responsible | Evidence Required | Pass Criteria | Related CRM Sheet | Status
Legal | Master Agreement signed | Yes | Before first job | Management | Signed agreement | Signed by authorised representative | Master Agreement Register | Pending
Territory | Cumilla Exclusivity accepted | Yes | Before Cumilla job | Management | Signed acknowledgement | Provider agrees all Cumilla work through Seventh Sky | Cumilla Register | Pending
Client Protection | Protected client obligations explained | Yes | Before first job | Provider Relationship Manager | Briefing record | Provider understands 24-month period | Protected Client Register | Pending
Compliance | Trade licence verified | Yes | Annual | Provider Relationship Manager | Licence copy | Valid/current | Compliance Register | Pending
Compliance | Electrical licence/certification verified | For installation | Annual | Operations Manager | Certificate | Valid/current | Compliance Register | Pending
Compliance | Engineering certification verified | If design/engineering | Annual | Operations Manager | Engineer credentials | Valid/current | Compliance Register | Pending
Insurance | Public liability verified | Yes | Annual | Provider Manager | Certificate | Current and adequate | Insurance Register | Pending
Insurance | Professional indemnity verified | If advice/design | Annual | Provider Manager | Certificate | Current and adequate | Insurance Register | Pending
Safety | Working at heights / electrical safety evidence | Yes | Annual + each job | Operations Manager | Training/safety checklist | No critical gap | Compliance Register | Pending
Operations | Work order accepted before work | Yes | Each job | Project Coordinator | Accepted work order | Accepted before site work | Work Order Register | Pending
Delivery | Progress photos and reports submitted | Yes | Each installation | Provider | Photos/reports | Complete | Installation Register | Pending
Delivery | Testing and commissioning report submitted | Yes | Each installation | Provider | Commissioning report | Complete | Testing Register | Pending
Warranty | Warranty documents supplied | Yes | Each project | Provider | Warranty certificates | Complete | Warranty Register | Pending
Finance | Provider invoice matches approved work order | Yes | Each job | Accounts | Invoice | Matches scope/variations | Payment Register | Pending

## Protected Client Register
Protected Client ID | Client Name | Client ID | Provider ID | Introduction Date | Protected Until | Last Work Order | Protection Basis | Direct Contact Allowed? | Breach Notes | Status
PC-0001 | Sample Residential Owner | SES-C0001 | SP-001 |  | 24 months after completion/termination | WO-0001 | Client introduced by Seventh Sky | No |  | Active
PC-0002 | Sample NRB Property Owner | SES-C0002 | SP-002 |  | 24 months after completion/termination | WO-0002 | Client assigned through Seventh Sky | No |  | Active
PC-0003 | Sample Small Business | SES-C0003 | SP-003 |  | 24 months after completion/termination | WO-0003 | Client coordinated by Seventh Sky | No |  | Active

## Complaint Register
Complaint ID | Date | Client ID | Project ID | Complaint Type | Description | Severity | Assigned To | Acknowledged Date | Resolution Due | Action Taken | Status | Outcome
COMP-0001 |  | SES-C0001 | SES-P0001 | Installation Quality | Example: client questions installation finish | Medium | Operations Manager |  |  | Investigate provider report/photos | Open
COMP-0002 |  | SES-C0002 | SES-P0002 | Battery Performance | Example: backup duration lower than expectation | High | Operations Manager |  |  | Review battery sizing and usage | Open

## Incident Register
Incident ID | Date | Project ID | Provider ID | Incident Type | Description | Severity | Immediate Action | Reported To | Corrective Action | Status | Lessons Learned
INC-0001 |  | SES-P0001 | SP-001 | Safety | Example: unsafe roof access identified | High | Stop work until access made safe | Operations Manager | Client/provider safety plan | Open
INC-0002 |  | SES-P0002 | SP-002 | Electrical/Battery | Example: battery placement ventilation concern | Critical | Pause battery installation | Operations Manager | Reassess location/fire safety | Open

## Risk Register
Risk ID | Risk Category | Description | Likelihood | Impact | Risk Rating | Mitigation | Owner | Review Date | Status
RISK-0001 | Performance | Client expects guaranteed energy savings/output/ROI | Medium | High | High | Use no-guarantee clauses and explain variables before agreement | Solar Consultant |  | Open
RISK-0002 | Safety | Electrical/fire/working-at-height risk during installation | Medium | High | High | Provider safety evidence, site assessment, incident reporting | Operations Manager |  | Open
RISK-0003 | Procurement | Equipment price/availability changes before approval | Medium | Medium | Medium | Quote validity and revised quote process | Project Coordinator |  | Open
RISK-0004 | Warranty | Manufacturer warranty claim rejected | Medium | Medium | Medium | Record warranties and claim process clearly | Coordinator |  | Open
RISK-0005 | Commercial | Provider bypasses Seventh Sky in Cumilla | Medium | High | High | Cumilla exclusivity, protected client register, monitoring | Director |  | Open

## Communication Log
Log ID | Date | Related To | Client/Provider ID | Project ID | Communication Type | Summary | Action Required | Responsible | Due Date | Status
COM-0001 |  | Client | SES-C0001 | SES-P0001 | Phone Call | Initial solar installation enquiry received | Collect electricity bill | Solar Consultant |  | Open
COM-0002 |  | Provider | SP-001 | SES-P0001 | Email/WhatsApp | Provider availability requested for site assessment | Confirm appointment | Project Coordinator |  | Open

## Project Closure Register
Closure ID | Project ID | Client ID | Completion Date | Final Payment Received | Warranty Registered | Handover Completed | Feedback Collected | Documents Archived | Closure Approved By | Status | Notes
CLOSE-0001 | SES-P0001 | SES-C0001 |  | No | No | No | No | No |  | Open
CLOSE-0002 | SES-P0003 | SES-C0003 |  | No | No | No | No | No |  | Open | Service project

## Improvement Register
Improvement ID | Source | Issue/Opportunity | Recommended Improvement | Responsible | Target Date | Status | Outcome
IMP-0001 | Client SOP | Need consistent handover records | Add automated handover checklist and document pack in CRM | Project Coordinator |  | Open
IMP-0002 | Provider SOP | Provider compliance may expire | Automate licence/insurance expiry alerts | CRM Developer/RENETECH |  | Open
IMP-0003 | Customer Agreement | No guarantee clauses need explanation | Add client acknowledgement checklist before agreement signing | Solar Consultant |  | Open
IMP-0004 | Operations | Warranty tracking manual risk | Automate warranty expiry and claim reminders | CRM Developer/RENETECH |  | Open

## KPI Dashboard Data
KPI | Target | Current Value | Data Source | Responsible | Review Frequency | Notes
Lead response time | Within 1 business day |  | Client Master Register | Solar Consultant | Weekly
Consultation completion | Within 2 business days |  | Client Needs Assessment | Solar Consultant | Weekly
Site assessment scheduled | Within 3 business days |  | Solar Site Assessment | Project Coordinator | Weekly
Quotation turnaround | Within 5 business days after assessment |  | Quotation Register | Solar Consultant | Weekly
Agreement signed before procurement | 100% |  | Agreement / Deposit Register | Operations Manager | Weekly | No procurement before required approval
Installation completion rate | 95%+ |  | Installation Register | Operations Manager | Monthly
Commissioning report received | 100% |  | Testing & Commissioning | Operations Manager | Weekly
Warranty registration | 100% |  | Warranty Register | Coordinator | Weekly
Complaint acknowledgement | Within 1 business day |  | Complaint Register | Operations Manager | Weekly
Provider compliance | 100% active providers compliant |  | Provider Compliance Register | Provider Manager | Monthly
Insurance compliance | 100% active providers insured |  | Provider Insurance Register | Provider Manager | Monthly
Cumilla exclusivity breaches | 0 |  | Cumilla / Protected Client Register | Director | Monthly
AMC/service plan conversion | Target 40%+ of installation clients |  | AMC Register | Solar Consultant | Monthly