## Dashboard
SEVENTH SKY PROPERTY CARE - WATER TANK CLEANING & MAINTENANCE CRM BLUEPRINT V2.0
Purpose | This workbook is a detailed CRM template and workflow checklist for Water Tank Cleaning & Maintenance Services.
Built From | Customer SOP, Third-Party SOP, Workflow/Checklist, Customer Service Agreement, Work Order and Service Provider Master Agreement.
CRM Systems | System 1: Client/End User Management. System 2: Third-Party Service Provider Management.
Key Controls | Cumilla exclusivity, protected client register, non-circumvention, insurance, compliance, AMC scheduling, complaint and incident tracking.
Automation Needed | Auto IDs, service status flow, work order generation, agreement population, AMC reminders, licence/insurance expiry reminders, payment reminders.
Recommended Use | Provide this workbook to RENETECH as the operational CRM blueprint for module development.
High-Level Workflow | Lead → Consultation → Site Assessment → Quote → Agreement → Deposit → Provider Assignment → Work Order → Service Delivery → Report → Invoice → AMC/Warranty → Closure.
Core Dashboards | Executive, Operations, Financial, AMC, Provider Compliance, Risk & Incident, Client Satisfaction.
Version | V2.0 - Populated detailed template
Prepared For | Seventh Sky Property Care
Status | Ready for CRM development discussion and further configuration.

## Lists & Status Values
List Type | Value | Use In Sheets | Notes
Lead Status | New Lead | Client Master Register | Initial enquiry received
Lead Status | Contacted | Client Master Register | Client contacted
Lead Status | Assessment Scheduled | Client Master Register / Site Assessment | Site assessment appointment confirmed
Lead Status | Quoted | Client Master Register / Quotation | Quotation issued
Lead Status | Agreement Sent | Agreement Register | Customer agreement sent
Lead Status | Agreement Signed | Agreement Register | Customer agreement executed
Lead Status | Work Order Issued | Work Order Register | Provider assigned
Project Status | Not Started | Project Register | No field work commenced
Project Status | In Progress | Project Register | Service delivery underway
Project Status | Waiting Client Approval | Quotation / Variation | Awaiting client confirmation
Project Status | Suspended | Project Register | Payment/access/safety/compliance issue
Project Status | Completed | Project Register | Service delivered
Project Status | Closed | Project Closure Register | All records completed
Priority | Low | Service Request / Complaint | Routine issue
Priority | Medium | Service Request / Complaint | Requires follow-up
Priority | High | Service Request / Complaint | Urgent operational issue
Priority | Critical | Complaint / Incident | Health, contamination, injury or major damage risk
Service Category | Residential Water Tank Cleaning | Service Request | Rooftop/underground/apartment/house tanks
Service Category | Water Tank Disinfection | Service Request | Sanitisation, bacteria/algae treatment
Service Category | Water Tank Inspection | Service Request | Internal condition, leakage, structural and water quality review
Service Category | Water Tank Repair | Service Request | Crack/leak/valve/pipe/tank refurbishment
Service Category | Water Supply System | Service Request | Pump/pipeline inspection and maintenance
Service Category | Water Quality Management | Service Request | Testing, contamination assessment, treatment support
Service Category | AMC Residential | AMC Register | Basic/Standard/Premium
Service Category | AMC Commercial | AMC Register | Building/hotel/restaurant/school/hospital package
Payment Status | Unpaid | Invoice & Payment Register | No payment received
Payment Status | Partial | Invoice & Payment Register | Part payment received
Payment Status | Paid | Invoice & Payment Register | Fully paid
Provider Status | Pending Onboarding | Provider Master Register | Initial provider profile
Provider Status | Approved | Provider Master Register | Eligible for work orders
Provider Status | Suspended | Provider Master Register | No new work order
Provider Status | Terminated | Provider Master Register | Inactive

## Client Master Register
Client ID | Project ID | Client Name | Client Type | Mobile | Email | NID/Passport/Company Reg | Service Address | District | Property Type | Lead Source | Requested Service | Current Status | Assigned Officer | Next Action | Next Follow-Up Date | Notes
WTCM-C0001 | WTCM-P0001 | Sample Residential Owner | Residential | 01XXXXXXXXX | client@example.com | NID pending | Cumilla Sadar, Cumilla | Cumilla | House | Website | Rooftop Water Tank Cleaning | New Lead | Client Service Coordinator | Call client and confirm tank details |  | Example only
WTCM-C0002 | WTCM-P0002 | Sample Apartment Committee | Residential Complex | 01XXXXXXXXX | committee@example.com | Committee docs pending | Kandirpar, Cumilla | Cumilla | Apartment Building | Referral | Apartment Water Tank Cleaning + Disinfection | Assessment Scheduled | Operations Coordinator | Assign provider for assessment |  | Example only
WTCM-C0003 | WTCM-P0003 | Sample Hospital | Commercial | 01XXXXXXXXX | admin@hospital.com | Trade licence pending | Dhaka | Dhaka | Hospital | Direct Call | Commercial AMC - School & Hospital Package | Quoted | Client Service Coordinator | Follow up quotation approval |  | Example only
WTCM-C0004 | WTCM-P0004 | Sample Restaurant | Commercial | 01XXXXXXXXX | restaurant@example.com | Trade licence pending | Cumilla | Cumilla | Restaurant | Facebook | Water Quality Testing + Tank Cleaning | Agreement Sent | Client Service Coordinator | Collect signed agreement and deposit |  | Example only

## Client Needs Assessment
Assessment ID | Client ID | Project ID | Tank Location | Tank Type | No. of Tanks | Estimated Capacity | Water Source | Known Issues | Water Quality Concern | Cleaning Frequency Needed | AMC Interested? | Emergency? | Client Notes | Recommended Next Step
NA-0001 | WTCM-C0001 | WTCM-P0001 | Rooftop | Plastic/RCC to confirm | 1 | 2000L approx. | Municipal | Algae smell | Yes | Annual | Yes - Basic | No | Client wants cleaning before family event | Book site assessment
NA-0002 | WTCM-C0002 | WTCM-P0002 | Rooftop + Underground | RCC | 3 | 10,000L total | Municipal + reserve | Sediment and bad smell | Yes | Six-monthly | Yes - Standard | No | Apartment committee requires report | Book assessment and quote
NA-0003 | WTCM-C0003 | WTCM-P0003 | Underground | RCC | 2 | 25,000L total | Municipal | Compliance concern | Yes | Quarterly | Yes - Commercial School/Hospital | No | Needs regular report and water monitoring | Prepare AMC proposal
NA-0004 | WTCM-C0004 | WTCM-P0004 | Rooftop | Plastic | 2 | 4000L total | Municipal | Food business hygiene concern | Yes | Quarterly | Yes - Hotel/Restaurant | Yes | Urgent cleaning requested | Send urgent provider work order

## Service Request Register
Request ID | Request Date | Client ID | Project ID | Service Category | Specific Service | Priority | Preferred Date | Site Visit Required | Customer Agreement Required | Deposit Required | Assigned Provider ID | Request Status | Remarks
SR-0001 |  | WTCM-C0001 | WTCM-P0001 | Residential Water Tank Cleaning | Rooftop Water Tank Cleaning | Medium |  | Yes | Yes | Yes |  | New | Collect access details
SR-0002 |  | WTCM-C0002 | WTCM-P0002 | Water Tank Disinfection | Apartment Water Tank Cleaning + Sanitisation | High |  | Yes | Yes | Yes |  | Assessment Scheduled | Need committee approval
SR-0003 |  | WTCM-C0003 | WTCM-P0003 | AMC Commercial | School & Hospital Package | High |  | Yes | Yes | Yes |  | Quoted | Include enhanced cleaning frequency
SR-0004 |  | WTCM-C0004 | WTCM-P0004 | Water Quality Management | Drinking Water Testing + Tank Cleaning | Critical |  | Yes | Yes | Yes |  | Agreement Sent | Food business priority

## Facility & Tank Register
Facility ID | Client ID | Project ID | Property Type | Site Address | Tank ID | Tank Location | Tank Material | Capacity | No. of Tanks | Access Condition | Water Source | Current Condition | Last Cleaning Date | Recommended Frequency
FAC-0001 | WTCM-C0001 | WTCM-P0001 | House | Cumilla Sadar | TANK-001 | Rooftop | Plastic/RCC to confirm | 2000L | 1 | Roof ladder required | Municipal | Unknown/dirty |  | Annual
FAC-0002 | WTCM-C0002 | WTCM-P0002 | Apartment Building | Kandirpar | TANK-002 | Underground | RCC | 5000L | 1 | Pump room access required | Municipal | Sediment suspected |  | Six-monthly
FAC-0003 | WTCM-C0002 | WTCM-P0002 | Apartment Building | Kandirpar | TANK-003 | Rooftop | RCC | 5000L | 2 | Roof access with safety check | Municipal | Algae suspected |  | Six-monthly
FAC-0004 | WTCM-C0003 | WTCM-P0003 | Hospital | Dhaka | TANK-004 | Underground | RCC | 25000L | 2 | Restricted access | Municipal | Requires hygiene monitoring |  | Quarterly

## Site Assessment Register
Assessment ID | Project ID | Client ID | Provider ID | Assessment Date | Tank Access Safe? | Confined Space Risk | Contamination Indicators | Leakage Status | Structural Condition | Overflow System | Pump/Pipeline Condition | Photos Collected | Recommended Scope | Variation Risk | Assessment Status
SA-0001 | WTCM-P0001 | WTCM-C0001 |  |  | To be checked | Low/Medium | Algae suspected | Unknown | Unknown | Unknown | Unknown | Pending | Cleaning + sanitisation | Low | Planned
SA-0002 | WTCM-P0002 | WTCM-C0002 |  |  | To be checked | Medium | Sediment + algae suspected | Unknown | Unknown | Needs check | Needs check | Pending | Deep cleaning + disinfection + report | Medium | Planned
SA-0003 | WTCM-P0003 | WTCM-C0003 |  |  | To be checked | High | Compliance review required | Unknown | Unknown | Needs check | Pump inspection required | Pending | Commercial AMC + water quality monitoring | High | Planned

## Quotation Register
Quote No | Project ID | Client ID | Service Description | Seventh Sky Fee | Provider Fee | Materials/Chemicals | Lab/Testing Fee | Transport | Other Cost | Total Quote | Validity | Issued Date | Client Decision | Approved Date | Notes
Q-0001 | WTCM-P0001 | WTCM-C0001 | Rooftop tank cleaning, sanitisation and basic inspection | BDT 2,000 | BDT 6,000 | BDT 1,500 | BDT 0 | BDT 1,000 | BDT 0 | BDT 10,500 | 14 days |  | Pending |  | Subject to site assessment
Q-0002 | WTCM-P0002 | WTCM-C0002 | Apartment rooftop/underground tank cleaning and disinfection | BDT 5,000 | BDT 18,000 | BDT 5,000 | BDT 0 | BDT 2,000 | BDT 0 | BDT 30,000 | 14 days |  | Pending |  | Committee approval required
Q-0003 | WTCM-P0003 | WTCM-C0003 | Commercial AMC - hospital package with water quality monitoring | BDT 20,000 | BDT 80,000 | BDT 15,000 | BDT 20,000 | BDT 5,000 | BDT 0 | BDT 140,000 | 30 days |  | Pending |  | Annual package

## Customer Agreement Register
Agreement ID | Project ID | Client ID | Agreement Type | Selected Services | Agreement Sent Date | Signed Date | Project Value | Payment Structure | Agreement Status | Storage Link | Remarks
CSA-0001 | WTCM-P0001 | WTCM-C0001 | Customer Service Agreement | Rooftop cleaning + sanitisation |  |  | BDT 10,500 | Deposit + final | Draft |  | Do not commence without signature
CSA-0002 | WTCM-P0002 | WTCM-C0002 | Customer Service Agreement | Apartment cleaning + disinfection |  |  | BDT 30,000 | 50% deposit + 50% completion | Pending Signature |  | Committee signatory required
CSA-0003 | WTCM-P0003 | WTCM-C0003 | Customer Service Agreement | Commercial AMC |  |  | BDT 140,000 | Quarterly/annual | Draft |  | AMC terms to be attached

## Work Order Register
WO No | Project ID | Client ID | Provider ID | Service Category | Scope Summary | Issue Date | Accepted Date | Start Date | Target Completion | Work Order Status | Provider Fee | Seventh Sky Fee | Warranty Required | Reports Required | Special Conditions
WO-0001 | WTCM-P0001 | WTCM-C0001 | WTP-001 | Residential Cleaning | Clean rooftop tank, sanitise, inspect overflow, provide before/after photos |  |  |  |  | Draft | BDT 6,000 | BDT 2,000 | Cleaning service warranty | Cleaning report + photos | Client remains protected
WO-0002 | WTCM-P0002 | WTCM-C0002 | WTP-001 | Apartment Cleaning | Clean underground and rooftop tanks, disinfect, provide completion report |  |  |  |  | Draft | BDT 18,000 | BDT 5,000 | Service warranty | Inspection report + photos | Committee approval required
WO-0003 | WTCM-P0003 | WTCM-C0003 | WTP-002 | Commercial AMC | Quarterly enhanced cleaning, monitoring and reports |  |  |  |  | Draft | BDT 80,000 | BDT 20,000 | AMC warranty | AMC report + water quality report | Hospital hygiene priority

## Project Register
Project ID | Client ID | Service Type | Assigned Provider | Project Stage | Start Date | Target Completion | Actual Completion | Progress % | Health/Risk | Latest Update | Next Action | Project Status
WTCM-P0001 | WTCM-C0001 | Residential Rooftop Cleaning |  | Lead/Assessment |  |  |  | 10% | Low | Needs site assessment | Book provider assessment | Open
WTCM-P0002 | WTCM-C0002 | Apartment Cleaning + Sanitisation |  | Assessment |  |  |  | 25% | Medium | Committee approval required | Send quote after site assessment | Open
WTCM-P0003 | WTCM-C0003 | Commercial AMC |  | Quotation |  |  |  | 35% | High | AMC proposal under review | Follow up client | Open

## Service Delivery Checklist
Checklist ID | Project ID | Service Stage | Checklist Item | Mandatory? | Responsible | Evidence Required | Completion Status | Notes
SDC-001 | WTCM-P0001 | Before Service | Customer agreement signed | Yes | Client Service Coordinator | Signed agreement | Pending | No work before signature
SDC-002 | WTCM-P0001 | Before Service | Deposit received | Yes | Accounts | Payment receipt | Pending | If applicable
SDC-003 | WTCM-P0001 | Before Service | Provider work order accepted | Yes | Operations Coordinator | Signed/accepted WO | Pending
SDC-004 | WTCM-P0001 | Before Service | Site access confirmed | Yes | Client Service Coordinator | Client confirmation | Pending
SDC-005 | WTCM-P0001 | During Service | Before photos uploaded | Yes | Provider | Photos | Pending
SDC-006 | WTCM-P0001 | During Service | Safety risks reviewed | Yes | Provider | Safety checklist | Pending
SDC-007 | WTCM-P0001 | During Service | Tank cleaning completed | Yes | Provider | Service report | Pending
SDC-008 | WTCM-P0001 | During Service | Disinfection completed where selected | If selected | Provider | Service report | Pending
SDC-009 | WTCM-P0001 | After Service | After photos uploaded | Yes | Provider | Photos | Pending
SDC-010 | WTCM-P0001 | After Service | Client sign-off obtained | Yes | Coordinator | Completion sign-off | Pending
SDC-011 | WTCM-P0001 | After Service | Invoice issued | Yes | Accounts | Invoice | Pending
SDC-012 | WTCM-P0001 | After Service | Warranty/AMC recommendation recorded | Yes | Coordinator | CRM note | Pending

## Water Quality Register
Test ID | Project ID | Client ID | Sample Date | Sample Location | Laboratory | Test Type | Result Summary | Contamination Found? | Follow-Up Required | Report Received | Report Link | Status
WQ-0001 | WTCM-P0004 | WTCM-C0004 |  | Kitchen/rooftop tank | To be selected | Drinking water testing | Pending | Unknown | Pending test | No |  | Planned
WQ-0002 | WTCM-P0003 | WTCM-C0003 |  | Hospital tank | To be selected | Water quality monitoring | Pending | Unknown | AMC monitoring | No |  | Planned

## Repair Register
Repair ID | Project ID | Client ID | Repair Type | Issue Description | Provider ID | Assessment Required | Estimated Cost | Client Approval | Repair Status | Warranty Period | Remarks
REP-0001 | WTCM-P0002 | WTCM-C0002 | Valve Replacement | Overflow valve may need replacement | WTP-001 | Yes | TBC | Pending | Not Started | TBC | Only if identified during assessment
REP-0002 | WTCM-P0003 | WTCM-C0003 | Pump/Pipeline Repair | Pump inspection required | WTP-002 | Yes | TBC | Pending | Not Started | TBC | Commercial facility

## Pump & Pipeline Register
Asset ID | Project ID | Client ID | Asset Type | Location | Condition | Last Inspection | Issue Identified | Recommended Action | Assigned Provider | Next Inspection | Status
PUMP-0001 | WTCM-P0003 | WTCM-C0003 | Water Pump | Hospital pump room | Unknown |  | To be inspected | Pump inspection under AMC | WTP-002 |  | Planned
PIPE-0001 | WTCM-P0002 | WTCM-C0002 | Water Line | Apartment building | Unknown |  | Leak detection if needed | Pipeline inspection | WTP-001 |  | Planned

## AMC Register
AMC ID | Client ID | Project ID | Package Type | Frequency | Start Date | End Date | Last Visit | Next Visit | Provider ID | Renewal Reminder | AMC Status | Inclusions
AMC-0001 | WTCM-C0001 | WTCM-P0001 | Residential Basic | Annual |  |  |  |  | WTP-001 |  | Proposed | Annual tank cleaning + inspection report
AMC-0002 | WTCM-C0002 | WTCM-P0002 | Residential Standard | Six-Monthly |  |  |  |  | WTP-001 |  | Proposed | Six-monthly cleaning + water quality inspection + maintenance report
AMC-0003 | WTCM-C0003 | WTCM-P0003 | School & Hospital Package | Quarterly |  |  |  |  | WTP-002 |  | Quoted | Enhanced cleaning frequency + water quality monitoring
AMC-0004 | WTCM-C0004 | WTCM-P0004 | Hotel & Restaurant Package | Quarterly |  |  |  |  | WTP-002 |  | Proposed | Regular cleaning + hygiene monitoring

## Invoice & Payment Register
Invoice No | Project ID | Client ID | Invoice Type | Invoice Amount | Due Date | Paid Amount | Outstanding Amount | Payment Status | Provider Payout Status | Receipt Link | Remarks
INV-0001 | WTCM-P0001 | WTCM-C0001 | Deposit | BDT 5,250 |  | BDT 0 | BDT 5,250 | Unpaid | Not Due |  | 50% deposit
INV-0002 | WTCM-P0001 | WTCM-C0001 | Final Payment | BDT 5,250 |  | BDT 0 | BDT 5,250 | Unpaid | Not Due |  | After completion
INV-0003 | WTCM-P0003 | WTCM-C0003 | AMC Payment | BDT 140,000 |  | BDT 0 | BDT 140,000 | Unpaid | Not Due |  | Annual AMC

## Warranty Register
Warranty ID | Project ID | Client ID | Provider ID | Warranty Type | Start Date | Expiry Date | Coverage | Exclusions | Claim Process | Warranty Status
WAR-0001 | WTCM-P0001 | WTCM-C0001 | WTP-001 | Cleaning Service Warranty |  |  | Cleaning workmanship only | Future contamination, municipal supply, client misuse excluded | Notify Seventh Sky in writing | Pending
WAR-0002 | WTCM-P0002 | WTCM-C0002 | WTP-001 | Disinfection Service Warranty |  |  | Disinfection service as performed | Future contamination excluded | Inspection may be required | Pending
WAR-0003 | WTCM-P0003 | WTCM-C0003 | WTP-002 | AMC Service Warranty |  |  | Services delivered under AMC package | Unapproved modifications excluded | Seventh Sky coordinates with provider | Pending

## Complaint Register
Complaint ID | Date | Client ID | Project ID | Complaint Type | Description | Severity | Assigned To | Acknowledged Date | Resolution Due | Action Taken | Status | Outcome
COMP-0001 |  | WTCM-C0001 | WTCM-P0001 | Service Quality | Example: client not satisfied with cleaning photos | Medium | Operations Manager |  |  | Investigate provider report | Open
COMP-0002 |  | WTCM-C0003 | WTCM-P0003 | Water Quality | Example: failed water test after service | Critical | Operations Manager |  |  | Escalate to lab/provider | Open

## Incident Register
Incident ID | Date | Project ID | Provider ID | Incident Type | Description | Severity | Immediate Action | Reported To | Corrective Action | Status | Lessons Learned
INC-0001 |  | WTCM-P0001 | WTP-001 | Safety | Example: unsafe rooftop access identified | High | Stop work until safe access confirmed | Operations Manager | Client to arrange safe access | Open
INC-0002 |  | WTCM-P0002 | WTP-001 | Property Damage | Example: pipe connection damage during cleaning | Medium | Photograph and investigate | Operations Manager | Provider to rectify if responsible | Open

## Provider Master Register
Provider ID | Business Name | Contact Person | Mobile | Email | Trade Licence | TIN | BIN | Approved Services | Coverage Area | Cumilla Exclusivity Signed | Master Agreement Status | Insurance Status | Provider Status | Assigned Manager | Notes
WTP-001 | Sample Tank Cleaning Provider | Provider Contact | 01XXXXXXXXX | provider@example.com | Pending | Pending | Pending | Cleaning, Disinfection, Basic Repairs | Dhaka/Cumilla through Seventh Sky | Yes | Active | Verified | Approved | Provider Relationship Manager | Example only
WTP-002 | Sample Water Quality & AMC Provider | Provider Contact | 01XXXXXXXXX | provider2@example.com | Pending | Pending | Pending | Water Testing, AMC, Commercial Facilities | Dhaka/Cumilla through Seventh Sky | Yes | Active | Pending | Conditional | Provider Relationship Manager | Collect insurance before work

## Provider Compliance Register
Provider ID | Compliance Item | Required | Evidence Required | Issue Date | Expiry Date | Verified By | Verification Date | Compliance Status | Follow-Up Action
WTP-001 | Trade Licence | Yes | Trade licence copy |  |  | Provider Relationship Manager |  | Pending | Collect before approval
WTP-001 | Company Registration | If company | Company registration certificate |  |  | Provider Relationship Manager |  | Pending | Collect
WTP-001 | TIN | Yes | TIN certificate |  |  | Accounts |  | Pending | Collect
WTP-001 | BIN | If applicable | BIN certificate |  |  | Accounts |  | N/A | Confirm applicability
WTP-001 | Safety Certification | Recommended | Safety training evidence |  |  | Operations Manager |  | Pending | Collect
WTP-001 | Water Quality Certification | If testing service | Certificate/lab authorisation |  |  | Operations Manager |  | N/A | Only if testing service assigned
WTP-002 | Water Testing Lab Approval | If testing | Lab certificate/approval |  |  | Operations Manager |  | Pending | Verify before testing
WTP-002 | Environmental Approval | If applicable | Environmental approval |  |  | Operations Manager |  | Pending | Assess requirement

## Provider Insurance Register
Provider ID | Insurance Type | Required? | Policy Number | Insurer | Coverage Amount | Expiry Date | Verified? | Reminder Date | Action Required
WTP-001 | Public Liability | Yes |  |  | BDT ______ |  | No |  | Mandatory before work order
WTP-001 | Workers Compensation | If employees |  |  | BDT ______ |  | No |  | Confirm workforce structure
WTP-001 | Contractor Insurance | Yes |  |  | BDT ______ |  | No |  | Collect certificate
WTP-001 | Vehicle Insurance | If vehicle used |  |  | BDT ______ |  | No |  | Collect if transport used
WTP-002 | Environmental Liability | If commercial/water quality |  |  | BDT ______ |  | No |  | Recommended
WTP-002 | Professional Indemnity | If testing/advice |  |  | BDT ______ |  | No |  | Required for professional advice

## Provider Capability Matrix
Provider ID | Rooftop Cleaning | Underground Cleaning | Apartment Tank Cleaning | Commercial Tank Cleaning | Sanitisation | Bacteria Treatment | Algae Treatment | Leakage Inspection | Structural Assessment | Crack Repair | Valve Replacement | Waterproofing | Pump Inspection | Pipeline Inspection | Water Testing | Water Treatment | Residential AMC | Commercial AMC | Emergency Response
WTP-001 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | No | Yes | Yes | No | No | Yes | Yes | Yes
WTP-002 | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No | Yes | Yes | Yes | Yes | No | Yes | Yes

## Provider Workflow Detailed
Phase | Step No | Workflow Step | Detailed Activity | Responsible | CRM Record | Required Evidence | Approval/Decision | Automation Opportunity | Output
Onboarding | 1 | Provider Application | Collect business profile, contact details, service categories and service area. | Provider Relationship Manager | Provider Master Register | Business profile | Proceed/Reject | Auto-create Provider ID | Provider profile created
Onboarding | 2 | Capability Review | Assess capability across cleaning, disinfection, repairs, water quality, pump/pipeline and AMC services. | Operations Manager | Provider Capability Matrix | Capability checklist | Approve categories | Dropdown service categories | Capability approved
Compliance | 3 | Licence Verification | Verify trade licence, registration, TIN, BIN, safety and water quality credentials. | Provider Relationship Manager | Provider Compliance Register | Documents | Compliant/Conditional | Expiry reminders | Compliance status updated
Compliance | 4 | Insurance Verification | Verify public liability, contractor, vehicle, workers compensation and professional indemnity where relevant. | Provider Relationship Manager | Provider Insurance Register | Insurance certificates | Approved/Not approved | Expiry reminders | Insurance status updated
Contracting | 5 | Master Agreement Signing | Issue and obtain signed Service Delivery Provider Master Agreement before any work assignment. | Management | Master Agreement Register | Signed agreement | Required before work | E-signature workflow | Provider legally onboarded
Territory Control | 6 | Cumilla Exclusivity Briefing | Explain protected client, non-circumvention and Cumilla exclusivity requirements. | Management | Cumilla Exclusivity Register | Acknowledgement | Must sign | Automated compliance reminder | Territory obligation recorded
Project Allocation | 7 | Client Scope Review | Review customer request and determine suitable provider based on capability and location. | Operations Coordinator | Service Request Register | Client request | Select provider | Auto-match provider by service | Provider selected
Project Allocation | 8 | Work Order Issue | Generate work order including client, site, service scope, price, timeline and reporting obligations. | Operations Coordinator | Work Order Register | Work order | Provider acceptance | Auto-populate from CRM | Work order issued
Delivery | 9 | Site Assessment | Provider inspects site, confirms risk, scope, access, variation and materials required. | Provider | Site Assessment Register | Assessment report/photos | Variation? | Mobile photo upload | Assessment completed
Delivery | 10 | Service Delivery | Provider completes cleaning, disinfection, repair, inspection, water testing, pump/pipeline or AMC service. | Provider | Project Register | Before/after photos | Quality review | Status updates | Service delivered
Quality | 11 | Completion Review | Operations checks report, photos, client feedback and warranty requirements. | Operations Manager | Service Delivery Checklist | Completion report | Approve/hold | Completion checklist | Project ready for invoice
Finance | 12 | Provider Payment | Accounts verifies client payment, provider invoice, approved costs and payout amount. | Accounts | Invoice & Payment Register | Invoice/receipt | Pay/Hold | Payment reminders | Payment processed
Post-Service | 13 | Warranty/AMC Tracking | Record warranties, next AMC visit, follow-up and renewal reminders. | Coordinator | Warranty/AMC Register | Warranty/AMC record | Ongoing support | Auto reminders | Lifecycle support active

## Provider Checklist
Checklist Category | Checklist Item | Mandatory? | Frequency | Responsible | Evidence Required | Pass Criteria | Related CRM Sheet | Status
Legal | Master Agreement signed | Yes | Before first job | Management | Signed agreement | Signed by authorised representative | Master Agreement Register | Pending
Territory | Cumilla Exclusivity acknowledgement | Yes | Before Cumilla job | Management | Signed acknowledgement | Provider agrees no direct Cumilla work | Cumilla Exclusivity Register | Pending
Client Protection | Protected client obligations explained | Yes | Before first job | Provider Relationship Manager | Training/briefing record | Provider understands 24-month protection | Protected Client Register | Pending
Compliance | Trade licence verified | Yes | Annual | Provider Relationship Manager | Licence copy | Valid/current | Provider Compliance Register | Pending
Compliance | TIN/BIN verified | Yes/If applicable | Annual | Accounts | Certificates | Valid/current | Provider Compliance Register | Pending
Insurance | Public liability verified | Yes | Annual | Provider Relationship Manager | Certificate | Current and adequate | Provider Insurance Register | Pending
Safety | Safety procedures confirmed | Yes | Annual + each job | Operations Manager | Safety checklist | No major risk unresolved | Incident Register | Pending
Operations | Work order accepted before work | Yes | Each job | Operations Coordinator | Accepted WO | Accepted by provider | Work Order Register | Pending
Delivery | Before and after photos provided | Yes | Each job | Provider | Photos | Clear and stored in CRM | Service Delivery Checklist | Pending
Delivery | Completion report submitted | Yes | Each job | Provider | Report | Complete and signed | Project Register | Pending
Quality | Client feedback collected | Yes | Each job | Coordinator | Feedback form | Satisfactory or actioned | Feedback Register | Pending
Finance | Provider invoice checked | Yes | Each job | Accounts | Invoice | Matches WO and approved variations | Invoice & Payment Register | Pending

## Cumilla Enquiry Referral
Referral ID | Provider ID | Enquiry Date | Enquiry Source | Prospective Client | Location | Service Requested | Referred to Seventh Sky Date | Provider Action | Compliance Status | Follow-Up Notes
CER-0001 | WTP-001 |  | Phone/Facebook/Referral | Example Cumilla Client | Cumilla | Tank Cleaning |  | Provider must refer to Seventh Sky | Pending | Any Cumilla lead must not be quoted directly
CER-0002 | WTP-002 |  | Website/Social Media | Example Commercial Client | Cumilla | Water Quality Testing |  | Provider must refer to Seventh Sky | Pending | Monitor compliance

## Protected Client Register
Protected Client ID | Client Name | Client ID | Provider ID | Introduction Date | Protected Until | Last Work Order | Protection Basis | Direct Contact Allowed? | Breach Notes | Status
PC-0001 | Sample Residential Owner | WTCM-C0001 | WTP-001 |  | 24 months after completion/termination | WO-0001 | Client introduced by Seventh Sky | No |  | Active
PC-0002 | Sample Apartment Committee | WTCM-C0002 | WTP-001 |  | 24 months after completion/termination | WO-0002 | Client assigned under work order | No |  | Active
PC-0003 | Sample Hospital | WTCM-C0003 | WTP-002 |  | 24 months after completion/termination | WO-0003 | Client coordinated by Seventh Sky | No |  | Active

## Communication Log
Log ID | Date | Related To | Client/Provider ID | Project ID | Communication Type | Summary | Action Required | Responsible | Due Date | Status
COM-0001 |  | Client | WTCM-C0001 | WTCM-P0001 | Phone Call | Initial enquiry received for rooftop cleaning | Schedule needs assessment | Client Service Coordinator |  | Open
COM-0002 |  | Provider | WTP-001 | WTCM-P0001 | WhatsApp/Email | Provider requested for availability | Confirm provider availability | Operations Coordinator |  | Open

## Risk Register
Risk ID | Risk Category | Description | Likelihood | Impact | Risk Rating | Mitigation | Owner | Review Date | Status
RISK-0001 | Health / Water Quality | Client assumes cleaning guarantees long-term drinking water quality | Medium | High | High | Use water quality disclaimer and recommend testing/AMC | Operations Manager |  | Open
RISK-0002 | Safety | Unsafe rooftop or confined-space access | Medium | High | High | Require site safety assessment before work | Operations Manager |  | Open
RISK-0003 | Commercial | Provider bypasses Seventh Sky in Cumilla | Medium | High | High | Use Cumilla exclusivity, protected client register and monitoring | Director |  | Open
RISK-0004 | Compliance | Provider insurance expired | Medium | High | High | Insurance expiry reminder and suspend work orders if expired | Provider Manager |  | Open

## Improvement Register
Improvement ID | Source | Issue/Opportunity | Recommended Improvement | Responsible | Target Date | Status | Outcome
IMP-0001 | Complaint | Client wants more transparent reporting | Add before/after photo upload requirement to CRM | Operations Manager |  | Open
IMP-0002 | Provider Audit | Provider documents expiry tracking manual | Add automated expiry reminders | CRM Developer/RENETECH |  | Open
IMP-0003 | AMC | Clients forget maintenance schedule | Automate AMC visit reminders | CRM Developer/RENETECH |  | Open

## KPI Dashboard Data
KPI | Target | Current Value | Data Source | Responsible | Review Frequency | Notes
Lead response time | Within 1 business day |  | Client Master Register | Client Service Coordinator | Weekly
Site assessment scheduled | Within 3 business days |  | Site Assessment Register | Operations Coordinator | Weekly
Quotation issued | Within 5 business days after assessment |  | Quotation Register | Client Service Coordinator | Weekly
Agreement signed before work | 100% |  | Customer Agreement Register | Operations Manager | Weekly | No work without agreement
Work order accepted before work | 100% |  | Work Order Register | Operations Coordinator | Weekly
Completion report received | 100% |  | Service Delivery Checklist | Operations Coordinator | Weekly
Complaint acknowledgement | Within 1 business day |  | Complaint Register | Operations Manager | Weekly
Provider compliance status | 100% current for active providers |  | Provider Compliance Register | Provider Manager | Monthly
Insurance compliance | 100% current for active providers |  | Provider Insurance Register | Provider Manager | Monthly
AMC renewal rate | 70%+ |  | AMC Register | Operations Manager | Monthly
Cumilla exclusivity breaches | 0 |  | Cumilla Enquiry Referral / Protected Client Register | Director | Monthly